## Sheet1
Area | Key Finding | Business Impact | Recommendation
55% Cost | 11 of the 20 projects are recorded as over budget | Immediate compression of net profit margins, restricted corporate cash flow, and potential shortfalls for upcoming Q4/Q1 pipeline initiatives. | Investigate cost variances, review estimates and approved changes, and monitor actual expenditure against budgets
70% Schedule | 14 of the 20 projects are recorded as behind schedule | Severely damages client relationships, risk of contractual late fees, and resource lock-in that prevents the teams from onboarding new revenue-generating accounts. | Review delayed activities, resource availability, subcontractor dependencies, and differences between planned and actual duration.
70% Data quality | 14 projects are marked either Review or Mismatch | Executive leadership is currently making strategic decisions based on flawed data. Operational blind spots are likely hiding deeper project failures | Reconcile recorded project statuses with progress percentages and confirm whether projects marked On Hold need separate treatment
2 Missing data | Two latest project records are classified as Missing Data in the budget-status pivot | Inability to calculate true return on investment (ROI) or forecast end-of-year financial performance accurately | Obtain the missing budget or actual cost figures before drawing conclusions about those projects' financial performance