## Sheet1
Step | Methodology
1. Data cleaning | Standardised project types, site locations, project statuses and contractor names. Corrected inconsistent text formatting.
2. Data quality checks | Checked Record_ID uniqueness, investigated a suspected duplicate record, and created flags for missing budget and actual cost data.
3. Calculated columns | Calculated schedule variance, cost variance, cost variance percentage, budget status, expected project status and status validation flags
4. Latest-record analysis | Identified the latest dated tracking record for each Project_ID to represent its latest recorded position.
5. Dashboard and recommendations | Created KPI cards and four charts, then documented business findings and recommendation follow-up actions
• Duplicate handling: Two records for PRJ-001 had the same latest date and appeared identical apart from Record_ID (REC-058 and REC-158).
• Limitations: The analysis represents the latest available tracking records, not necessarily verified final project outcomes. Missing cost data and status inconsistencies may affect interpretation.