## Sheet1
Record_ID | Project_ID | Project_Name | Site_Location | Project_Type | Project_Manager | Main_Contractor | Material_Category | Start_Date | Planned_Duration_Days | Actual_Duration_Days | Budget_ZAR | Actual_Cost_ZAR | Progress_Percent | Project_Status | Last_Updated
REC-001 | PRJ-004 | Oak Residences | Cape Town | Residential | B. Mokoena | Mandla Construction | Cement | 2025-01-13 | 90 | 90 | 1645067.11 |  |  | Planning | 2025-06-17
REC-002 | PRJ-001 | Summit Residences | Johannesburg | Renovation | C. Naidoo | CapeBuild | Steel | 2025-10-15 | 70 | 100 | 4311777.74 | 4538019.91 | 40 | On Hold | 2025-12-10
REC-003 | PRJ-011 | Central Mall | Pretoria | Residential |  | CapeBuild | Roofing | 2025-02-22 | 43 | 52 |  | 1028574.72 | 55 | Planning | 2025-07-31
REC-004 | PRJ-012 | Riverside Mall | Pretoria | Roadworks | D. Smith | CapeBuild | Steel | 2025-10-23 | 69 | 99 | 684719.68 | 760471.35 | 55 | ON HOLD | 2026-01-26
REC-005 | PRJ-012 | Metro Depot | Pretoria | Roadworks | E. Dlamini | Mandla Construction | Roofing | 2025-04-18 | 88 | 117 | 6104091.17 | 6739024.65 | 25 | In Progress
REC-006 | PRJ-002 | Riverside Depot | Pretoria | Renovation | B. Mokoena | CapeBuild | Steel | 2025-04-28 | 28 | 64 | 2221581.55 | 2030237.7 | 40 | Completed
REC-007 | PRJ-018 | Riverside Road Upgrade | Gqeberha | Renovation | A. Jacobs | BuildRight Ltd | Concrete | 2025-10-03 | 87 | 119 | 3903662.44 | 4797255.44 | 85 | Completed | 2025-11-12
REC-008 | PRJ-006 | Harbour Mall | Gqeberha | Roadworks | C. Naidoo | BuildRight Ltd | Bricks | 2025-08-05 | 172 | 161 | 2654795.7 | 2861721.66 | 100 | Completed | 2025-11-25
REC-009 | PRJ-006 | Cedar School | Gqeberha | Infrastructure | B. Mokoena | Mandla Construction | Bricks | 2025-08-21 | 20 | 51 | 5724080.88 | 5218613.2 |  | In Progress | 2025-10-02
REC-010 | PRJ-018 | Riverside Residences | Johannesburg | Infrastructure | A. Jacobs | BuildRight Ltd | Roofing | 2025-09-29 | 20 | 43 | 2275975.36 | 1797425.07 | 70 | Completed | 2026-02-01
REC-011 | PRJ-003 | Oak Clinic | Gqeberha | residential | C. Naidoo | UrbanWorks | Roofing | 2025-09-30 | 52 | 45 | 4373442.64 | 5481779.45 |  | Complete | 2026-03-16
REC-012 | PRJ-012 | Riverside Clinic | Cape Town | Residential | A. Jacobs | Mandla Construction | Concrete | 2025-08-13 | 152 | 165 | 1006276.22 | 897949.25 | 70 | Planning | 2025-08-22
REC-013 | PRJ-011 | Central Clinic | Pretoria | Renovation | B. Mokoena | BuildRight Ltd | Concrete | 2025-02-06 | 151 | 151 | 1990482.9 | 2035681.29 |  | ON HOLD | 2025-07-25
REC-014 | PRJ-014 | Oak Office Block | Cape Town | Commercial | B. Mokoena | Mandla Construction | Cement | 2025-07-01 | 128 | 139 | 3168904.18 | 3626931.01 | 10 | Planning | 2025-10-24
REC-015 | PRJ-005 | Cedar Residences | Gqeberha | Residential | A. Jacobs | Build Right Ltd | Steel | 2025-08-05 | 66 | 68 |  | 3823878.04 | 10 | On Hold | 2025-11-18
REC-016 | PRJ-016 | Oak School | Pretoria | Renovation | D. Smith | Ndlovu Projects | Roofing | 2025-09-04 | 74 | 114 | 2756501.83 | 2230885.72 | 85 | Planning | 2026-01-07
REC-017 | PRJ-005 | Greenfield Residences | Cape Town | Infrastructure | D. Smith | Ndlovu Projects | Cement | 2025-04-08 | 95 | 93 | 6304433.53 | 6743159.98 |  | Planning | 2025-05-19
REC-018 | PRJ-002 | Cedar Clinic | Gqeberha | Infrastructure | A. Jacobs | Ndlovu Projects | Concrete | 2025-09-18 | 40 | 79 | 1411406.01 | 1520814.75 | 40 | On Hold | 2026-01-04
REC-019 | PRJ-019 | Summit Bridge | Johannesburg | COMMERCIAL | D. Smith | CapeBuild | Concrete | 2025-10-17 | 153 | 158 | 6091914.11 |  | 70 | in progress | 2025-10-20
REC-020 | PRJ-015 | Greenfield Mall | Johannesburg | Roadworks |  | Mandla Construction | Timber | 2025-11-15 | 164 | 155 | 707879.51 | 627589.8 | 55 | In Progress | 2026-04-04
REC-021 | PRJ-010 | Summit Mall | Cape Town | residential | B. Mokoena | CapeBuild | Bricks | 2025-11-10 | 155 | 140 | 4424145.02 | 4677653.58 | 10 | In Progress | 2026-04-14
REC-022 | PRJ-007 | Harbour Mall | Pretoria | Roadworks | A. Jacobs | BuildRight Ltd | Bricks | 2025-06-25 | 72 | 100 | 4213987.24 | 3843122.44 | 100 | Completed | 2025-07-29
REC-023 | PRJ-009 | Metro Residences | Durban | Infrastructure | E. Dlamini | Mandla Construction | Timber | 2025-03-24 | 133 | 153 | 4660421.54 | 4942160.02 | 10 | Planning | 2025-04-26
REC-024 | PRJ-002 | Riverside Clinic | Cape Town | Roadworks | E. Dlamini | UrbanWorks | Cement | 2025-06-07 | 113 | 155 | 6081800.07 | 7700155.71 |  | Completed | 2025-07-17
REC-025 | PRJ-008 | Riverside School | CAPETOWN | Residential | D. Smith | BuildRight Ltd | Timber | 2025-03-25 | 65 | 106 | 2826840.06 | 2458447.2 | 70 | On Hold | 2025-05-21
REC-026 | PRJ-007 | Riverside Bridge | Durban | Roadworks | A. Jacobs | CapeBuild | Bricks | 2025-08-24 | 109 | 113 | 5378352.38 | 6538256.02 | 40 | Planning
REC-027 | PRJ-017 | Summit Residences | Cape Town | Infrastructure | D. Smith | CapeBuild | Roofing | 2025-07-24 | 157 | 163 | 6120232.13 | 5126740.21 | 55 | In Progress | 2025-10-13
REC-028 | PRJ-014 | Oak Residences | Gqeberha | Infrastructure |  | CapeBuild | Timber | 2025-11-07 | 150 | 142 | 2657471.46 | 2838960.87 | 55 | Planning | 2025-11-25
REC-029 | PRJ-011 | Oak Office Block | Pretoria | Roadworks | E. Dlamini | Mandla Construction | Steel | 2025-11-16 | 100 | 127 | 5550095.5 | 6326426.94 | 55 | completed | 2026-03-04
REC-030 | PRJ-013 | Summit Clinic | Durban | Infrastructure | E. Dlamini | CapeBuild | Timber | 2025-03-31 | 177 | 198 | 2130936.72 | 2245940.41 | 0 | Completed | 2025-07-23
REC-031 | PRJ-015 | Summit Office Block |  | Commercial | C. Naidoo |  | Steel | 2025-04-20 | 150 | 165 | 5210846.24 |  | 75% | Planning | 2025-05-28
REC-032 | PRJ-001 | Riverside Bridge | Pretoria | Renovation | B. Mokoena | Mandla Construction | Roofing | 2025-01-24 | 82 | 97 | 4070462.33 | 4739014.07 | 100 | On Hold | 2025-07-20
REC-033 | PRJ-001 | Harbour Clinic | Cape Town | Renovation |  | UrbanWorks | Roofing | 2025-02-24 | 128 | 127 | 1349291.76 | 1698735.42 |  | On Hold | 2025-07-10
REC-034 | PRJ-018 | Central Road Upgrade | Pretoria | Renovation | C. Naidoo | Mandla Construction | Roofing | 2025-11-01 | 101 | 146 | 4970312.58 | 4976707.94 |  | On Hold | 2026-01-11
REC-035 | PRJ-017 | Summit Office Block | Durban | Renovation | A. Jacobs | Mandla Construction | Steel | 2025-09-06 | 180 | 180 | 1966234.04 | 1609837.76 | 55 | In Progress | 2025-11-05
REC-036 | PRJ-013 | Harbour Clinic | Pretoria | Renovation | E. Dlamini | BuildRight Ltd | Cement | 2025-03-20 | 74 | 63 | 2842924.35 | 2687816.37 | 100 | On Hold | 2025-06-26
REC-037 | PRJ-016 | Central Clinic |  | Road Works | D. Smith |  | Timber | 2025-01-04 | 110 | 114 | 4959219.53 | 5984409.11 | 85 | In Progress | 2025-04-01
REC-038 | PRJ-013 | Harbour Mall | Pretoria | Commercial | D. Smith | Mandla Construction | Concrete | 2025-03-26 | 139 | 182 | 1047673.73 |  | 0 | On Hold
REC-039 | PRJ-013 | Oak School | Cape Town | Renovation | A. Jacobs | Build Right Ltd | Concrete | 2025-06-17 | 74 | 88 | 2292786.28 | 2661041.81 | 85 | Completed | 2025-09-15
REC-040 | PRJ-008 | Riverside Road Upgrade | Durban | Residential | E. Dlamini | Mandla Construction | Timber | 2025-02-05 | 30 | 63 | 443937.49 | 401160.41 | 0 | In Progress
REC-041 | PRJ-009 | Summit Mall | Gqeberha | Residential | C. Naidoo | Ndlovu Projects | Roofing | 2025-07-08 | 62 | 85 | 4045296.84 | 4668122.17 | 10 | Complete
REC-042 | PRJ-013 | Cedar Residences | Durban | Infrastructure | D. Smith | CapeBuild | Concrete | 2025-04-12 | 39 | 61 | 4566340.1 | 4993846.33 | 10 | Completed | 2025-08-20
REC-043 | PRJ-011 | Metro Bridge | Johannesburg | Infrastructure | C. Naidoo | Ndlovu Projects | Cement | 2025-01-07 | 127 | 164 | 3313760.66 | 3303029.71 | 70 | in progress | 2025-05-11
REC-044 | PRJ-015 | Central Clinic | Pretoria | Infrastructure | E. Dlamini | UrbanWorks | Bricks | 2025-12-08 | 171 | 173 | 2264403.64 | 2044184.92 | 10 | Completed | 2025-08-20
REC-045 | PRJ-016 | Summit Residences | Gqeberha | Commercial | A. Jacobs | Mandla Construction | Roofing | 2025-06-16 | 66 | 82 | 1575749.06 | 1857676.06 | 70 | Completed | 2025-09-29
REC-046 | PRJ-016 | Cedar School | Johannesburg | Renovation | B. Mokoena | CapeBuild | Roofing | 2025-10-12 | 81 | 110 | 3225581.94 | 3664006.92 | unknown | Planning | 2026-03-10
REC-047 | PRJ-012 | Greenfield Depot | Durban | Roadworks | C. Naidoo | Mandla Construction | Concrete | 2025-08-31 | 161 | 179 | 2398483.71 | 3066019.46 |  | Completed | 2025-10-20
REC-048 | PRJ-011 | Summit School |  | Commercial | C. Naidoo | Mandla Construction | Bricks | 2025-03-03 | 157 | 202 | 5013685.06 | 4374815.85 | 40 | in progress | 2025-04-18
REC-049 | PRJ-010 | Metro Depot | Cape Town | Residential | E. Dlamini | CapeBuild | Timber | 2025-01-08 | 156 | 149 | 1964445.79 | 2489242.5 |  | Completed | 2025-05-11
REC-050 | PRJ-015 | Oak Depot | Cape Town | Infrastructure | A. Jacobs | Mandla Construction | Steel | 2025-06-24 | 67 | 55 | 1827989.94 | 2213442.61 | 10 | Planning | 2025-11-16
REC-051 | PRJ-010 | Central Depot | Durban | Infrastructure | D. Smith | CapeBuild | Cement | 2025-02-13 | 83 | 75 | 3737956.47 | 3693426.23 | 40 | On Hold | 2025-07-22
REC-052 | PRJ-002 | Metro Clinic | Johannesburg | Infrastructure | A. Jacobs | Mandla Construction | Concrete | 2025-11-09 | 45 | 90 | 5017106.9 | 5482481.27 | 55 | Planning | 2026-02-22
REC-053 | PRJ-015 | Cedar Clinic | Durban | Infrastructure | B. Mokoena | UrbanWorks | Concrete | 2025-11-01 | 140 | 143 | 453999.1 | 419518.98 | 55 | On Hold | 2026-03-21
REC-054 | PRJ-008 | Central Mall | Pretoria | Roadworks | D. Smith | CapeBuild | Cement | 2025-03-18 | 88 | 125 | 1138976.78 | 922365.06 |  | Completed | 2025-08-04
REC-055 | PRJ-016 | Harbour Mall | Johannesburg | Infrastructure | E. Dlamini | Build Right Ltd | Roofing | 2025-08-13 | 40 | 63 | 499129.9 |  | 70 | Completed | 2025-10-21
REC-056 | PRJ-019 | Oak Depot | Cape Town | Renovation | C. Naidoo | UrbanWorks | Bricks | 2025-01-21 | 64 | 79 | 3493524.01 | 3497418.25 | 55 | In Progress | 2025-04-14
REC-057 | PRJ-004 | Central Mall | cape town | Roadworks | C. Naidoo | BuildRight Ltd | Timber | 2025-03-24 | 104 | 115 | 4585460.46 | 4237464.81 | 85 | Planning | 2025-08-03
REC-058 | PRJ-001 | Harbour Clinic | Durban | Infra-structure | B. Mokoena | CapeBuild | Timber | 2025-10-05 | 138 | 149 | 588775.53 | 611867.13 | 100 | On Hold | 2026-04-02
REC-059 | PRJ-016 | Harbour Bridge | Cape Town | Commercial | A. Jacobs | UrbanWorks | Concrete | 2025-03-04 | 27 | 52 | 4055447.92 | 3648478.58 | 25 | Completed | 2025-08-17
REC-060 | PRJ-005 | Riverside Depot | Durban | Commercial | D. Smith | Mandla Construction | Cement | 2025-09-13 | 94 | 111 | 4658822.69 | 4601729.62 | 100 | On Hold | 2026-01-22
REC-061 | PRJ-005 | Harbour School | CAPETOWN | Infrastructure | E. Dlamini | UrbanWorks | Steel | 2025-02-05 | 90 | 124 | 5187538.64 | 5122545.07 |  | Completed | 2025-05-31
REC-062 | PRJ-018 | Riverside Clinic | Gqeberha | Renovation | B. Mokoena | UrbanWorks | Concrete | 2025-09-05 | 108 | 114 | 3699483.86 | 3890802.78 | 100 | Completed | 2025-11-26
REC-063 | PRJ-016 | Harbour Road Upgrade | Gqeberha | Infrastructure | C. Naidoo | BuildRight Ltd | Timber | 2025-07-15 | 118 | 145 | 5202460.38 | 5753970.61 | 25 | On Hold | 2025-08-10
REC-064 | PRJ-017 | Central School | Durban | Infrastructure | D. Smith | BuildRight Ltd | Bricks | 2025-08-22 | 23 | 54 |  | 1398967.1 | 25 | Planning | 2026-02-11
REC-065 | PRJ-018 | Cedar Clinic | Durban | Commercial | A. Jacobs | UrbanWorks | Concrete | 2025-07-14 | 101 | 126 | 4741983.91 | 5499283.03 |  | Planning | 2025-12-24
REC-066 | PRJ-004 | Summit Office Block | Durban | Road Works | B. Mokoena | Mandla Construction | Cement | 2025-08-16 | 62 | 91 |  | 1685605.29 | 70 | Planning
REC-067 | PRJ-019 | Metro Clinic | Pretoria | COMMERCIAL | D. Smith | CapeBuild | Roofing | 2025-04-03 | 63 | 59 | 743552.19 | 903728.05 | 40 | On Hold | 2025-04-06
REC-068 | PRJ-015 | Summit Depot | Durban | Commercial |  | UrbanWorks | Concrete | 2025-05-28 | 159 | 154 | 711636.88 | 891409.04 | 75% | On Hold | 2025-07-28
REC-069 | PRJ-013 | Summit Residences |  | Residential | E. Dlamini | UrbanWorks | Bricks | 2025-10-20 | 111 | 132 |  | 2371342.08 | 0 | On Hold | 2025-12-18
REC-070 | PRJ-020 | Harbour School | Pretoria | Residential | E. Dlamini | CapeBuild | Roofing | 2025-06-30 | 76 | 101 | 1438324.93 | 1302134.83 | 25 | Planning | 2025-08-03
REC-071 | PRJ-003 | Summit Road Upgrade | Durban | Renovation |  | CapeBuild | Concrete | 2025-06-01 | 103 | 135 | 2846894.33 | 2506398.36 |  | Completed | 2025-09-29
REC-072 | PRJ-003 | Cedar Bridge | Cape Town | Roadworks | E. Dlamini | BuildRight Ltd | Timber | 2025-03-14 | 77 | 117 | 4477023.28 | 5001744.36 | 85 | Completed | 2025-06-17
REC-073 | PRJ-009 | Harbour Office Block | Gqeberha | Commercial | A. Jacobs | UrbanWorks | Roofing | 2025-10-27 | 117 | 154 | 4240932.92 | 4095625.07 | 40 | On Hold | 2026-01-13
REC-074 | PRJ-014 | Cedar Clinic | JHB | Commercial | D. Smith | UrbanWorks | Bricks | 2025-03-01 | 55 | 42 |  | 5746097.1 |  | Planning | 2025-08-20
REC-075 | PRJ-018 | Oak School | Cape Town | Roadworks | B. Mokoena | UrbanWorks | Timber | 2025-08-03 | 170 | 202 | 4791244.69 | 5858287.9 | 10 | On Hold | 2025-10-03
REC-076 | PRJ-012 | Summit Clinic | Cape Town | Renovation | A. Jacobs | Mandla Construction | Roofing | 2025-02-20 | 114 | 133 | 5885601.33 | 6488365.8 | 0 | On Hold | 2025-08-03
REC-077 | PRJ-020 | Riverside Clinic | Johannesburg | Roadworks | B. Mokoena | Ndlovu Projects | Concrete | 2025-01-11 | 32 | 67 |  | 2975024.83 | 40 | Planning | 2025-03-23
REC-078 | PRJ-005 | Harbour Office Block | Johannesburg | Infrastructure |  | BuildRight Ltd | Steel | 2025-03-08 | 158 | 159 | 5240711.4 | 4375801.02 | 0 | In Progress | 2025-05-15
REC-079 | PRJ-002 | Cedar Depot | Gqeberha | Commercial | E. Dlamini | BuildRight Ltd | Roofing | 2025-03-06 | 127 | 145 | 960308.17 |  | 100 | Completed | 2025-08-22
REC-080 | PRJ-017 | Oak Mall | Pretoria | Renovation | A. Jacobs | BuildRight Ltd | Bricks | 2025-06-04 | 137 | 163 | 6275163.64 | 5085472.33 | 100 | On Hold | 2025-11-07
REC-081 | PRJ-005 | Summit Depot | Gqeberha | Infrastructure | D. Smith | BuildRight Ltd | Roofing | 2025-02-03 | 52 | 54 |  | 4453760.3 | 70 | On Hold | 2025-03-05
REC-082 | PRJ-018 | Oak Mall | Durban | Renovation | C. Naidoo | CapeBuild | Bricks | 2025-04-21 | 130 | 143 | 5800568.89 | 5724620.8 | 100 | On Hold | 2025-05-31
REC-083 | PRJ-016 | Harbour Office Block | Cape Town | Renovation | C. Naidoo | UrbanWorks | Roofing | 2025-04-02 | 43 | 81 | 783527.23 | 780344.75 | 70 | In Progress | 2025-02-18
REC-084 | PRJ-010 | Riverside Mall | Durban | Infrastructure | C. Naidoo | BuildRight Ltd | Bricks | 2025-11-04 | 99 | 106 | 897503.54 | 927755.04 | 25 | Hold | 2026-03-31
REC-085 | PRJ-008 | Summit Residences | Johannesburg | Roadworks | C. Naidoo | CapeBuild | Bricks | 2025-08-08 | 163 | 197 | 5365167.87 | 5830792.76 |  | Planning | 2025-08-10
REC-086 | PRJ-006 | Riverside Bridge | Pretoria | Renovation | C. Naidoo | Mandla Construction | Bricks | 2025-03-15 | 164 | 191 | 2754902.15 | 2344249.07 |  | Planning | 2025-06-03
REC-087 | PRJ-011 | Summit Depot | CAPETOWN | Renovation | E. Dlamini | UrbanWorks | Timber | 2025-10-18 | 172 | 162 | 5770888.65 | 4950210.3 | 0 | Planning | 2025-12-27
REC-088 | PRJ-007 | Harbour Clinic | Pretoria | Infrastructure | A. Jacobs | BuildRight Ltd | Steel | 2025-09-20 | 49 | 56 | 2936960.21 | 2706770.77 | 100 | Completed | 2025-12-07
REC-089 | PRJ-007 | Metro Bridge | Gqeberha | Commercial | E. Dlamini | Ndlovu Projects | Roofing | 2025-03-12 | 85 | 88 | 2300764.72 | 1803488.83 | 85 | In Progress | 2025-06-11
REC-090 | PRJ-003 | Oak Bridge | Durban | Residential | D. Smith | BuildRight Ltd | Bricks | 2025-07-23 | 30 | 42 | 367134.6 | 455460.29 | 70 | On Hold | 2025-09-05
REC-091 | PRJ-020 | Cedar Bridge | Durban | Roadworks | B. Mokoena | CapeBuild | Steel | 2025-08-24 | 112 | 102 | 2979448.62 | 2481676.81 | 85 | On Hold | 2025-09-13
REC-092 | PRJ-017 | Metro Clinic | Cape Town | residential | C. Naidoo | Mandla Construction | Steel | 2025-11-21 | 49 | 67 | 3437200.39 |  | 70 | ON HOLD | 2026-04-25
REC-093 | PRJ-005 | Greenfield Road Upgrade | Pretoria | Residential | D. Smith | UrbanWorks | Roofing | 2025-02-08 | 65 | 110 | 5080300.56 | 5217765.94 | 100 | Completed | 2025-04-27
REC-094 | PRJ-009 | Harbour Office Block | Durban | Residential |  | Ndlovu Projects | Cement | 2025-10-30 | 34 | 41 | 3420855.53 | 3199197.52 | 100 | Planning | 2026-03-09
REC-095 | PRJ-013 | Riverside Office Block | Gqeberha | Renovation | E. Dlamini | Mandla Construction | Concrete | 2025-08-25 | 168 | 188 | 6213946.73 | 7142686.46 | 0 | On Hold | 2025-12-19
REC-096 | PRJ-004 | Metro Office Block | Durban | Roadworks | D. Smith | UrbanWorks | Bricks | 2025-06-25 | 41 | 58 | 4288294.32 | 3428796.05 | 100 | On Hold | 2025-12-16
REC-097 | PRJ-020 | Summit Road Upgrade | Durban | Residential | E. Dlamini | Mandla Construction | Bricks | 2025-01-27 | 105 | 94 | 2310567.22 | 2446848.19 | 85 | Completed | 2025-04-17
REC-098 | PRJ-013 | Metro Mall | Pretoria | Renovation | C. Naidoo | BuildRight Ltd | Bricks | 2025-03-08 | 172 | 202 | 6112513.75 | 5713922.5 | 85 | Completed | 2025-05-27
REC-099 | PRJ-006 | Cedar School | JHB | Infrastructure | E. Dlamini | Ndlovu Projects | Concrete | 2025-04-20 | 107 | 152 | 5038476.3 | 4413718.42 | 25 | In Progress | 2025-10-07
REC-158 | PRJ-001 | Harbour Clinic | Durban | Infra-structure | B. Mokoena | CapeBuild | Timber | 2025-10-05 | 138 | 149 | 588775.53 | 611867.13 | 100 | On Hold | 2026-04-02