## Raw_Data
Record_ID | Project_ID | Project_Name | Site_Location | Project_Type | Project_Manager | Main_Contractor | Material_Category | Start_Date | Planned_Duration_Days | Actual_Duration_Days | Budget_ZAR | Actual_Cost_ZAR | Progress_Percent | Project_Status | Last_Updated
REC-001 | PRJ-004 | Oak Residences | Cape Town | Residential | B. Mokoena | Mandla Construction | Cement | 2025-01-13 | 90 | 90 | 1645067.11 |  |  | Planning | 2025-06-17
REC-002 | PRJ-001 | Summit Residences | Johannesburg | Renovation | C. Naidoo | CapeBuild | Steel | 2025-10-15 | 70 | 100 | 4311777.74 | 4538019.91 | 40 | On Hold | 2025-12-10
REC-003 | PRJ-011 | Central Mall | Pretoria | Residential |  | CapeBuild | Roofing | 2025-02-22 | 43 | 52 |  | 1028574.72 | 55 | Planning | 2025-07-31
REC-004 | PRJ-012 | Riverside Mall | Pretoria | Roadworks | D. Smith | CapeBuild | Steel | 2025-10-23 | 69 | 99 | 684719.68 | 760471.35 | 55 | ON HOLD | 2026-01-26
REC-005 | PRJ-012 | Metro Depot | Pretoria | Roadworks | E. Dlamini | Mandla Construction | Roofing | 2025-04-18 | 88 | 117 | 6104091.17 | 6739024.65 | 25 | In Progress
REC-006 | PRJ-002 | Riverside Depot | Pretoria | Renovation | B. Mokoena | CapeBuild | Steel | 2025-04-28 | 28 | 64 | 2221581.55 | 2030237.7 | 40 | Completed
REC-007 | PRJ-018 | Riverside Road Upgrade | Gqeberha | Renovation | A. Jacobs | BuildRight Ltd | Concrete | 2025-10-03 | 87 | 119 | 3903662.44 | 4797255.44 | 85 | Completed | 2025-11-12
REC-008 | PRJ-006 | Harbour Mall | Gqeberha | Roadworks | C. Naidoo | BuildRight Ltd | Bricks | 2025-08-05 | 172 | 161 | 2654795.7 | 2861721.66 | 100 | Completed | 2025-11-25
REC-009 | PRJ-006 | Cedar School | Gqeberha | Infrastructure | B. Mokoena | Mandla Construction | Bricks | 2025-08-21 | 20 | 51 | 5724080.88 | 5218613.2 |  | In Progress | 2025-10-02
REC-010 | PRJ-018 | Riverside Residences | Johannesburg | Infrastructure | A. Jacobs | BuildRight Ltd | Roofing | 2025-09-29 | 20 | 43 | 2275975.36 | 1797425.07 | 70 | Completed | 2026-02-01
REC-011 | PRJ-003 | Oak Clinic | Gqeberha | residential | C. Naidoo | UrbanWorks | Roofing | 2025-09-30 | 52 | 45 | 4373442.64 | 5481779.45 |  | Complete | 2026-03-16
REC-012 | PRJ-012 | Riverside Clinic | Cape Town | Residential | A. Jacobs | Mandla Construction | Concrete | 2025-08-13 | 152 | 165 | 1006276.22 | 897949.25 | 70 | Planning | 2025-08-22
REC-013 | PRJ-011 | Central Clinic | Pretoria | Renovation | B. Mokoena | BuildRight Ltd | Concrete | 2025-02-06 | 151 | 151 | 1990482.9 | 2035681.29 |  | ON HOLD | 2025-07-25
REC-014 | PRJ-014 | Oak Office Block | Cape Town | Commercial | B. Mokoena | Mandla Construction | Cement | 2025-07-01 | 128 | 139 | 3168904.18 | 3626931.01 | 10 | Planning | 2025-10-24
REC-015 | PRJ-005 | Cedar Residences | Gqeberha | Residential | A. Jacobs | Build Right Ltd | Steel | 2025-08-05 | 66 | 68 |  | 3823878.04 | 10 | On Hold | 2025-11-18
REC-016 | PRJ-016 | Oak School | Pretoria | Renovation | D. Smith | Ndlovu Projects | Roofing | 2025-09-04 | 74 | 114 | 2756501.83 | 2230885.72 | 85 | Planning | 2026-01-07
REC-017 | PRJ-005 | Greenfield Residences | Cape Town | Infrastructure | D. Smith | Ndlovu Projects | Cement | 2025-04-08 | 95 | 93 | 6304433.53 | 6743159.98 |  | Planning | 2025-05-19
REC-018 | PRJ-002 | Cedar Clinic | Gqeberha | Infrastructure | A. Jacobs | Ndlovu Projects | Concrete | 2025-09-18 | 40 | 79 | 1411406.01 | 1520814.75 | 40 | On Hold | 2026-01-04
REC-019 | PRJ-019 | Summit Bridge | Johannesburg | COMMERCIAL | D. Smith | CapeBuild | Concrete | 2025-10-17 | 153 | 158 | 6091914.11 |  | 70 | in progress | 2025-10-20
REC-020 | PRJ-015 | Greenfield Mall | Johannesburg | Roadworks |  | Mandla Construction | Timber | 2025-11-15 | 164 | 155 | 707879.51 | 627589.8 | 55 | In Progress | 2026-04-04
REC-021 | PRJ-010 | Summit Mall | Cape Town | residential | B. Mokoena | CapeBuild | Bricks | 2025-11-10 | 155 | 140 | 4424145.02 | 4677653.58 | 10 | In Progress | 2026-04-14
REC-022 | PRJ-007 | Harbour Mall | Pretoria | Roadworks | A. Jacobs | BuildRight Ltd | Bricks | 2025-06-25 | 72 | 100 | 4213987.24 | 3843122.44 | 100 | Completed | 2025-07-29
REC-023 | PRJ-009 | Metro Residences | Durban | Infrastructure | E. Dlamini | Mandla Construction | Timber | 2025-03-24 | 133 | 153 | 4660421.54 | 4942160.02 | 10 | Planning | 2025-04-26
REC-024 | PRJ-002 | Riverside Clinic | Cape Town | Roadworks | E. Dlamini | UrbanWorks | Cement | 2025-06-07 | 113 | 155 | 6081800.07 | 7700155.71 |  | Completed | 2025-07-17
REC-025 | PRJ-008 | Riverside School | CAPETOWN | Residential | D. Smith | BuildRight Ltd | Timber | 2025-03-25 | 65 | 106 | 2826840.06 | 2458447.2 | 70 | On Hold | 2025-05-21
REC-026 | PRJ-007 | Riverside Bridge | Durban | Roadworks | A. Jacobs | CapeBuild | Bricks | 2025-08-24 | 109 | 113 | 5378352.38 | 6538256.02 | 40 | Planning
REC-027 | PRJ-017 | Summit Residences | Cape Town | Infrastructure | D. Smith | CapeBuild | Roofing | 2025-07-24 | 157 | 163 | 6120232.13 | 5126740.21 | 55 | In Progress | 2025-10-13
REC-028 | PRJ-014 | Oak Residences | Gqeberha | Infrastructure |  | CapeBuild | Timber | 2025-11-07 | 150 | 142 | 2657471.46 | 2838960.87 | 55 | Planning | 2025-11-25
REC-029 | PRJ-011 | Oak Office Block | Pretoria | Roadworks | E. Dlamini | Mandla Construction | Steel | 2025-11-16 | 100 | 127 | 5550095.5 | 6326426.94 | 55 | completed | 2026-03-04
REC-030 | PRJ-013 | Summit Clinic | Durban | Infrastructure | E. Dlamini | CapeBuild | Timber | 2025-03-31 | 177 | 198 | 2130936.72 | 2245940.41 | 0 | Completed | 2025-07-23
REC-031 | PRJ-015 | Summit Office Block |  | Commercial | C. Naidoo |  | Steel | 2025-04-20 | 150 | 165 | 5210846.24 |  | 75% | Planning | 2025-05-28
REC-032 | PRJ-001 | Riverside Bridge | Pretoria | Renovation | B. Mokoena | Mandla Construction | Roofing | 2025-01-24 | 82 | 97 | 4070462.33 | 4739014.07 | 100 | On Hold | 2025-07-20
REC-033 | PRJ-001 | Harbour Clinic | Cape Town | Renovation |  | UrbanWorks | Roofing | 2025-02-24 | 128 | 127 | 1349291.76 | 1698735.42 |  | On Hold | 2025-07-10
REC-034 | PRJ-018 | Central Road Upgrade | Pretoria | Renovation | C. Naidoo | Mandla Construction | Roofing | 2025-11-01 | 101 | 146 | 4970312.58 | 4976707.94 |  | On Hold | 2026-01-11
REC-035 | PRJ-017 | Summit Office Block | Durban | Renovation | A. Jacobs | Mandla Construction | Steel | 2025-09-06 | 180 | 180 | 1966234.04 | 1609837.76 | 55 | In Progress | 2025-11-05
REC-036 | PRJ-013 | Harbour Clinic | Pretoria | Renovation | E. Dlamini | BuildRight Ltd | Cement | 2025-03-20 | 74 | 63 | 2842924.35 | 2687816.37 | 100 | On Hold | 2025-06-26
REC-037 | PRJ-016 | Central Clinic |  | Road Works | D. Smith |  | Timber | 2025-01-04 | 110 | 114 | 4959219.53 | 5984409.11 | 85 | In Progress | 2025-04-01
REC-038 | PRJ-013 | Harbour Mall | Pretoria | Commercial | D. Smith | Mandla Construction | Concrete | 2025-03-26 | 139 | 182 | 1047673.73 |  | 0 | On Hold
REC-039 | PRJ-013 | Oak School | Cape Town | Renovation | A. Jacobs | Build Right Ltd | Concrete | 2025-06-17 | 74 | 88 | 2292786.28 | 2661041.81 | 85 | Completed | 2025-09-15
REC-040 | PRJ-008 | Riverside Road Upgrade | Durban | Residential | E. Dlamini | Mandla Construction | Timber | 2025-02-05 | 30 | 63 | 443937.49 | 401160.41 | 0 | In Progress
REC-041 | PRJ-009 | Summit Mall | Gqeberha | Residential | C. Naidoo | Ndlovu Projects | Roofing | 2025-07-08 | 62 | 85 | 4045296.84 | 4668122.17 | 10 | Complete
REC-042 | PRJ-013 | Cedar Residences | Durban | Infrastructure | D. Smith | CapeBuild | Concrete | 2025-04-12 | 39 | 61 | 4566340.1 | 4993846.33 | 10 | Completed | 2025-08-20
REC-043 | PRJ-011 | Metro Bridge | Johannesburg | Infrastructure | C. Naidoo | Ndlovu Projects | Cement | 2025-01-07 | 127 | 164 | 3313760.66 | 3303029.71 | 70 | in progress | 2025-05-11
REC-044 | PRJ-015 | Central Clinic | Pretoria | Infrastructure | E. Dlamini | UrbanWorks | Bricks | 2025-12-08 | 171 | 173 | 2264403.64 | 2044184.92 | 10 | Completed | 2025-08-20
REC-045 | PRJ-016 | Summit Residences | Gqeberha | Commercial | A. Jacobs | Mandla Construction | Roofing | 2025-06-16 | 66 | 82 | 1575749.06 | 1857676.06 | 70 | Completed | 2025-09-29
REC-046 | PRJ-016 | Cedar School | Johannesburg | Renovation | B. Mokoena | CapeBuild | Roofing | 2025-10-12 | 81 | 110 | 3225581.94 | 3664006.92 | unknown | Planning | 2026-03-10
REC-047 | PRJ-012 | Greenfield Depot | Durban | Roadworks | C. Naidoo | Mandla Construction | Concrete | 2025-08-31 | 161 | 179 | 2398483.71 | 3066019.46 |  | Completed | 2025-10-20
REC-048 | PRJ-011 | Summit School |  | Commercial | C. Naidoo | Mandla Construction | Bricks | 2025-03-03 | 157 | 202 | 5013685.06 | 4374815.85 | 40 | in progress | 2025-04-18
REC-049 | PRJ-010 | Metro Depot | Cape Town | Residential | E. Dlamini | CapeBuild | Timber | 2025-01-08 | 156 | 149 | 1964445.79 | 2489242.5 |  | Completed | 2025-05-11
REC-050 | PRJ-015 | Oak Depot | Cape Town | Infrastructure | A. Jacobs | Mandla Construction | Steel | 2025-06-24 | 67 | 55 | 1827989.94 | 2213442.61 | 10 | Planning | 2025-11-16
REC-051 | PRJ-010 | Central Depot | Durban | Infrastructure | D. Smith | CapeBuild | Cement | 2025-02-13 | 83 | 75 | 3737956.47 | 3693426.23 | 40 | On Hold | 2025-07-22
REC-052 | PRJ-002 | Metro Clinic | Johannesburg | Infrastructure | A. Jacobs | Mandla Construction | Concrete | 2025-11-09 | 45 | 90 | 5017106.9 | 5482481.27 | 55 | Planning | 2026-02-22
REC-053 | PRJ-015 | Cedar Clinic | Durban | Infrastructure | B. Mokoena | UrbanWorks | Concrete | 2025-11-01 | 140 | 143 | 453999.1 | 419518.98 | 55 | On Hold | 2026-03-21
REC-054 | PRJ-008 | Central Mall | Pretoria | Roadworks | D. Smith | CapeBuild | Cement | 2025-03-18 | 88 | 125 | 1138976.78 | 922365.06 |  | Completed | 2025-08-04
REC-055 | PRJ-016 | Harbour Mall | Johannesburg | Infrastructure | E. Dlamini | Build Right Ltd | Roofing | 2025-08-13 | 40 | 63 | 499129.9 |  | 70 | Completed | 2025-10-21
REC-056 | PRJ-019 | Oak Depot | Cape Town | Renovation | C. Naidoo | UrbanWorks | Bricks | 2025-01-21 | 64 | 79 | 3493524.01 | 3497418.25 | 55 | In Progress | 2025-04-14
REC-057 | PRJ-004 | Central Mall | cape town | Roadworks | C. Naidoo | BuildRight Ltd | Timber | 2025-03-24 | 104 | 115 | 4585460.46 | 4237464.81 | 85 | Planning | 2025-08-03
REC-058 | PRJ-001 | Harbour Clinic | Durban | Infra-structure | B. Mokoena | CapeBuild | Timber | 2025-10-05 | 138 | 149 | 588775.53 | 611867.13 | 100 | On Hold | 2026-04-02
REC-059 | PRJ-016 | Harbour Bridge | Cape Town | Commercial | A. Jacobs | UrbanWorks | Concrete | 2025-03-04 | 27 | 52 | 4055447.92 | 3648478.58 | 25 | Completed | 2025-08-17
REC-060 | PRJ-005 | Riverside Depot | Durban | Commercial | D. Smith | Mandla Construction | Cement | 2025-09-13 | 94 | 111 | 4658822.69 | 4601729.62 | 100 | On Hold | 2026-01-22
REC-061 | PRJ-005 | Harbour School | CAPETOWN | Infrastructure | E. Dlamini | UrbanWorks | Steel | 2025-02-05 | 90 | 124 | 5187538.64 | 5122545.07 |  | Completed | 2025-05-31
REC-062 | PRJ-018 | Riverside Clinic | Gqeberha | Renovation | B. Mokoena | UrbanWorks | Concrete | 2025-09-05 | 108 | 114 | 3699483.86 | 3890802.78 | 100 | Completed | 2025-11-26
REC-063 | PRJ-016 | Harbour Road Upgrade | Gqeberha | Infrastructure | C. Naidoo | BuildRight Ltd | Timber | 2025-07-15 | 118 | 145 | 5202460.38 | 5753970.61 | 25 | On Hold | 2025-08-10
REC-064 | PRJ-017 | Central School | Durban | Infrastructure | D. Smith | BuildRight Ltd | Bricks | 2025-08-22 | 23 | 54 |  | 1398967.1 | 25 | Planning | 2026-02-11
REC-065 | PRJ-018 | Cedar Clinic | Durban | Commercial | A. Jacobs | UrbanWorks | Concrete | 2025-07-14 | 101 | 126 | 4741983.91 | 5499283.03 |  | Planning | 2025-12-24
REC-066 | PRJ-004 | Summit Office Block | Durban | Road Works | B. Mokoena | Mandla Construction | Cement | 2025-08-16 | 62 | 91 |  | 1685605.29 | 70 | Planning
REC-067 | PRJ-019 | Metro Clinic | Pretoria | COMMERCIAL | D. Smith | CapeBuild | Roofing | 2025-04-03 | 63 | 59 | 743552.19 | 903728.05 | 40 | On Hold | 2025-04-06
REC-068 | PRJ-015 | Summit Depot | Durban | Commercial |  | UrbanWorks | Concrete | 2025-05-28 | 159 | 154 | 711636.88 | 891409.04 | 75% | On Hold | 2025-07-28
REC-069 | PRJ-013 | Summit Residences |  | Residential | E. Dlamini | UrbanWorks | Bricks | 2025-10-20 | 111 | 132 |  | 2371342.08 | 0 | On Hold | 2025-12-18
REC-070 | PRJ-020 | Harbour School | Pretoria | Residential | E. Dlamini | CapeBuild | Roofing | 2025-06-30 | 76 | 101 | 1438324.93 | 1302134.83 | 25 | Planning | 2025-08-03
REC-071 | PRJ-003 | Summit Road Upgrade | Durban | Renovation |  | CapeBuild | Concrete | 2025-06-01 | 103 | 135 | 2846894.33 | 2506398.36 |  | Completed | 2025-09-29
REC-072 | PRJ-003 | Cedar Bridge | Cape Town | Roadworks | E. Dlamini | BuildRight Ltd | Timber | 2025-03-14 | 77 | 117 | 4477023.28 | 5001744.36 | 85 | Completed | 2025-06-17
REC-073 | PRJ-009 | Harbour Office Block | Gqeberha | Commercial | A. Jacobs | UrbanWorks | Roofing | 2025-10-27 | 117 | 154 | 4240932.92 | 4095625.07 | 40 | On Hold | 2026-01-13
REC-074 | PRJ-014 | Cedar Clinic | JHB | Commercial | D. Smith | UrbanWorks | Bricks | 2025-03-01 | 55 | 42 |  | 5746097.1 |  | Planning | 2025-08-20
REC-075 | PRJ-018 | Oak School | Cape Town | Roadworks | B. Mokoena | UrbanWorks | Timber | 2025-08-03 | 170 | 202 | 4791244.69 | 5858287.9 | 10 | On Hold | 2025-10-03
REC-076 | PRJ-012 | Summit Clinic | Cape Town | Renovation | A. Jacobs | Mandla Construction | Roofing | 2025-02-20 | 114 | 133 | 5885601.33 | 6488365.8 | 0 | On Hold | 2025-08-03
REC-077 | PRJ-020 | Riverside Clinic | Johannesburg | Roadworks | B. Mokoena | Ndlovu Projects | Concrete | 2025-01-11 | 32 | 67 |  | 2975024.83 | 40 | Planning | 2025-03-23
REC-078 | PRJ-005 | Harbour Office Block | Johannesburg | Infrastructure |  | BuildRight Ltd | Steel | 2025-03-08 | 158 | 159 | 5240711.4 | 4375801.02 | 0 | In Progress | 2025-05-15
REC-079 | PRJ-002 | Cedar Depot | Gqeberha | Commercial | E. Dlamini | BuildRight Ltd | Roofing | 2025-03-06 | 127 | 145 | 960308.17 |  | 100 | Completed | 2025-08-22
REC-080 | PRJ-017 | Oak Mall | Pretoria | Renovation | A. Jacobs | BuildRight Ltd | Bricks | 2025-06-04 | 137 | 163 | 6275163.64 | 5085472.33 | 100 | On Hold | 2025-11-07
REC-081 | PRJ-005 | Summit Depot | Gqeberha | Infrastructure | D. Smith | BuildRight Ltd | Roofing | 2025-02-03 | 52 | 54 |  | 4453760.3 | 70 | On Hold | 2025-03-05
REC-082 | PRJ-018 | Oak Mall | Durban | Renovation | C. Naidoo | CapeBuild | Bricks | 2025-04-21 | 130 | 143 | 5800568.89 | 5724620.8 | 100 | On Hold | 2025-05-31
REC-083 | PRJ-016 | Harbour Office Block | Cape Town | Renovation | C. Naidoo | UrbanWorks | Roofing | 2025-04-02 | 43 | 81 | 783527.23 | 780344.75 | 70 | In Progress | 2025-02-18
REC-084 | PRJ-010 | Riverside Mall | Durban | Infrastructure | C. Naidoo | BuildRight Ltd | Bricks | 2025-11-04 | 99 | 106 | 897503.54 | 927755.04 | 25 | Hold | 2026-03-31
REC-085 | PRJ-008 | Summit Residences | Johannesburg | Roadworks | C. Naidoo | CapeBuild | Bricks | 2025-08-08 | 163 | 197 | 5365167.87 | 5830792.76 |  | Planning | 2025-08-10
REC-086 | PRJ-006 | Riverside Bridge | Pretoria | Renovation | C. Naidoo | Mandla Construction | Bricks | 2025-03-15 | 164 | 191 | 2754902.15 | 2344249.07 |  | Planning | 2025-06-03
REC-087 | PRJ-011 | Summit Depot | CAPETOWN | Renovation | E. Dlamini | UrbanWorks | Timber | 2025-10-18 | 172 | 162 | 5770888.65 | 4950210.3 | 0 | Planning | 2025-12-27
REC-088 | PRJ-007 | Harbour Clinic | Pretoria | Infrastructure | A. Jacobs | BuildRight Ltd | Steel | 2025-09-20 | 49 | 56 | 2936960.21 | 2706770.77 | 100 | Completed | 2025-12-07
REC-089 | PRJ-007 | Metro Bridge | Gqeberha | Commercial | E. Dlamini | Ndlovu Projects | Roofing | 2025-03-12 | 85 | 88 | 2300764.72 | 1803488.83 | 85 | In Progress | 2025-06-11
REC-090 | PRJ-003 | Oak Bridge | Durban | Residential | D. Smith | BuildRight Ltd | Bricks | 2025-07-23 | 30 | 42 | 367134.6 | 455460.29 | 70 | On Hold | 2025-09-05
REC-091 | PRJ-020 | Cedar Bridge | Durban | Roadworks | B. Mokoena | CapeBuild | Steel | 2025-08-24 | 112 | 102 | 2979448.62 | 2481676.81 | 85 | On Hold | 2025-09-13
REC-092 | PRJ-017 | Metro Clinic | Cape Town | residential | C. Naidoo | Mandla Construction | Steel | 2025-11-21 | 49 | 67 | 3437200.39 |  | 70 | ON HOLD | 2026-04-25
REC-093 | PRJ-005 | Greenfield Road Upgrade | Pretoria | Residential | D. Smith | UrbanWorks | Roofing | 2025-02-08 | 65 | 110 | 5080300.56 | 5217765.94 | 100 | Completed | 2025-04-27
REC-094 | PRJ-009 | Harbour Office Block | Durban | Residential |  | Ndlovu Projects | Cement | 2025-10-30 | 34 | 41 | 3420855.53 | 3199197.52 | 100 | Planning | 2026-03-09
REC-095 | PRJ-013 | Riverside Office Block | Gqeberha | Renovation | E. Dlamini | Mandla Construction | Concrete | 2025-08-25 | 168 | 188 | 6213946.73 | 7142686.46 | 0 | On Hold | 2025-12-19
REC-096 | PRJ-004 | Metro Office Block | Durban | Roadworks | D. Smith | UrbanWorks | Bricks | 2025-06-25 | 41 | 58 | 4288294.32 | 3428796.05 | 100 | On Hold | 2025-12-16
REC-097 | PRJ-020 | Summit Road Upgrade | Durban | Residential | E. Dlamini | Mandla Construction | Bricks | 2025-01-27 | 105 | 94 | 2310567.22 | 2446848.19 | 85 | Completed | 2025-04-17
REC-098 | PRJ-013 | Metro Mall | Pretoria | Renovation | C. Naidoo | BuildRight Ltd | Bricks | 2025-03-08 | 172 | 202 | 6112513.75 | 5713922.5 | 85 | Completed | 2025-05-27
REC-099 | PRJ-006 | Cedar School | JHB | Infrastructure | E. Dlamini | Ndlovu Projects | Concrete | 2025-04-20 | 107 | 152 | 5038476.3 | 4413718.42 | 25 | In Progress | 2025-10-07
REC-158 | PRJ-001 | Harbour Clinic | Durban | Infra-structure | B. Mokoena | CapeBuild | Timber | 2025-10-05 | 138 | 149 | 588775.53 | 611867.13 | 100 | On Hold | 2026-04-02

## Cleaned Data
Record_ID | Project_ID | Project_Name | Site_Location | Project_Type | Project_Manager | Main_Contractor | Material_Category | Start_Date | Planned_Duration_Days | Actual_Duration_Days | Budget_ZAR | Budget_Missing | Actual_Cost_ZAR | Actual_Missing | Cost_Data _Flag | Progress_Percent | Project_Status | Project_Expected_Status | Project_Status_Check | Last_Updated | Schedule_Variance | Schedule_Status | Cost_Variance | Cost_Variance_Percentage | Budget_Status | Cost_Variance_Pivot | Cost_Variance_Percentage_Pivot | Latest_Record_Flag | Valid_Date_Count | Latest_Count | Record_Review_Flag | Latest_Record_Check
REC-001 | PRJ-004 | Oak Residences | Cape Town | Residential | B. Mokoena | Mandla Construction | Cement | 2025-01-13 | 90 | 90 | 1645067.11 | Present |  | Missing | Actual Cost Missing |  | Planning | Planning | OK | 2025-06-17 | 0 | On Schedule |  |  | Missing Data | 0 | 0% | Older | 3 | 1 | Unique
REC-002 | PRJ-001 | Summit Residences | Johannesburg | Renovation | C. Naidoo | CapeBuild | Steel | 2025-10-15 | 70 | 100 | 4311777.74 | Present | 4538019.91 | Present | Complete | 40 | On Hold | In Progress | Review | 2025-12-10 | 30 | Behind Schedule | 226242.17 | 5.247% | Over Budget | 226242.17 | 5.247% | Older | 4 | 1 | Unique
REC-003 | PRJ-011 | Central Mall | Pretoria | Residential | Unknown | CapeBuild | Roofing | 2025-02-22 | 43 | 52 |  | Missing | 1028574.72 | Present | Budget Missing | 55 | Planning | In Progress | Mismatch | 2025-07-31 | 9 | Behind Schedule | 1028574.72 |  | Missing Data | 0 | 0% | Older | 6 | 1 | Unique
REC-004 | PRJ-012 | Riverside Mall | Pretoria | Roadworks | D. Smith | CapeBuild | Steel | 2025-10-23 | 69 | 99 | 684719.68 | Present | 760471.35 | Present | Complete | 55 | On Hold | In Progress | Review | 2026-01-26 | 30 | Behind Schedule | 75751.67 | 11.06% | Over Budget | 75751.67 | 11.06% | Latest | 4 | 1 | Unique | OK
REC-005 | PRJ-012 | Metro Depot | Pretoria | Roadworks | E. Dlamini | Mandla Construction | Roofing | 2025-04-18 | 88 | 117 | 6104091.17 | Present | 6739024.65 | Present | Complete | 25 | In Progress | In Progress | OK |  | 29 | Behind Schedule | 634933.48 | 10.4% | Over Budget | 634933.48 | 10.4% | Missing Date | 4 | 1 | Unique
REC-006 | PRJ-002 | Riverside Depot | Pretoria | Renovation | B. Mokoena | CapeBuild | Steel | 2025-04-28 | 28 | 64 | 2221581.55 | Present | 2030237.7 | Present | Complete | 40 | Completed | In Progress | Mismatch |  | 36 | Behind Schedule | -191343.85 | -8.613% | Under Budget | -191343.85 | -8.613% | Missing Date | 4 | 1 | Unique
REC-007 | PRJ-018 | Riverside Road Upgrade | Gqeberha | Renovation | A. Jacobs | BuildRight Ltd | Concrete | 2025-10-03 | 87 | 119 | 3903662.44 | Present | 4797255.44 | Present | Complete | 85 | Completed | In Progress | Mismatch | 2025-11-12 | 32 | Behind Schedule | 893593 | 22.89% | Over Budget | 893593 | 22.89% | Older | 7 | 1 | Unique
REC-008 | PRJ-006 | Harbour Mall | Gqeberha | Roadworks | C. Naidoo | BuildRight Ltd | Bricks | 2025-08-05 | 172 | 161 | 2654795.7 | Present | 2861721.66 | Present | Complete | 100 | Completed | Completed | OK | 2025-11-25 | -11 | Ahead of Schedule | 206925.96 | 7.794% | Over Budget | 206925.96 | 7.794% | Latest | 4 | 1 | Unique | OK
REC-009 | PRJ-006 | Cedar School | Gqeberha | Infrastructure | B. Mokoena | Mandla Construction | Bricks | 2025-08-21 | 20 | 51 | 5724080.88 | Present | 5218613.2 | Present | Complete |  | In Progress | Planning | Mismatch | 2025-10-02 | 31 | Behind Schedule | -505467.68 | -8.831% | Under Budget | -505467.68 | -8.831% | Older | 4 | 1 | Unique
REC-010 | PRJ-018 | Riverside Residences | Johannesburg | Infrastructure | A. Jacobs | BuildRight Ltd | Roofing | 2025-09-29 | 20 | 43 | 2275975.36 | Present | 1797425.07 | Present | Complete | 70 | Completed | In Progress | Mismatch | 2026-02-01 | 23 | Behind Schedule | -478550.29 | -21.03% | Under Budget | -478550.29 | -21.03% | Latest | 7 | 1 | Unique | OK
REC-011 | PRJ-003 | Oak Clinic | Gqeberha | Residential | C. Naidoo | UrbanWorks | Roofing | 2025-09-30 | 52 | 45 | 4373442.64 | Present | 5481779.45 | Present | Complete |  | Completed | Planning | Mismatch | 2026-03-16 | -7 | Ahead of Schedule | 1108336.81 | 25.34% | Over Budget | 1108336.81 | 25.34% | Latest | 4 | 1 | Unique | OK
REC-012 | PRJ-012 | Riverside Clinic | Cape Town | Residential | A. Jacobs | Mandla Construction | Concrete | 2025-08-13 | 152 | 165 | 1006276.22 | Present | 897949.25 | Present | Complete | 70 | Planning | In Progress | Mismatch | 2025-08-22 | 13 | Behind Schedule | -108326.97 | -10.77% | Under Budget | -108326.97 | -10.77% | Older | 4 | 1 | Unique
REC-013 | PRJ-011 | Central Clinic | Pretoria | Renovation | B. Mokoena | BuildRight Ltd | Concrete | 2025-02-06 | 151 | 151 | 1990482.9 | Present | 2035681.29 | Present | Complete |  | On Hold | Planning | Review | 2025-07-25 | 0 | On Schedule | 45198.39 | 2.271% | Over Budget | 45198.39 | 2.271% | Older | 6 | 1 | Unique
REC-014 | PRJ-014 | Oak Office Block | Cape Town | Commercial | B. Mokoena | Mandla Construction | Cement | 2025-07-01 | 128 | 139 | 3168904.18 | Present | 3626931.01 | Present | Complete | 10 | Planning | Planning | OK | 2025-10-24 | 11 | Behind Schedule | 458026.83 | 14.45% | Over Budget | 458026.83 | 14.45% | Older | 3 | 1 | Unique
REC-015 | PRJ-005 | Cedar Residences | Gqeberha | Residential | A. Jacobs | BuildRight Ltd | Steel | 2025-08-05 | 66 | 68 |  | Missing | 3823878.04 | Present | Budget Missing | 10 | On Hold | Planning | Review | 2025-11-18 | 2 | Behind Schedule | 3823878.04 |  | Missing Data | 0 | 0% | Older | 7 | 1 | Unique
REC-016 | PRJ-016 | Oak School | Pretoria | Renovation | D. Smith | Ndlovu Projects | Roofing | 2025-09-04 | 74 | 114 | 2756501.83 | Present | 2230885.72 | Present | Complete | 85 | Planning | In Progress | Mismatch | 2026-01-07 | 40 | Behind Schedule | -525616.11 | -19.07% | Under Budget | -525616.11 | -19.07% | Older | 8 | 1 | Unique
REC-017 | PRJ-005 | Greenfield Residences | Cape Town | Infrastructure | D. Smith | Ndlovu Projects | Cement | 2025-04-08 | 95 | 93 | 6304433.53 | Present | 6743159.98 | Present | Complete |  | Planning | Planning | OK | 2025-05-19 | -2 | Ahead of Schedule | 438726.45 | 6.959% | Over Budget | 438726.45 | 6.959% | Older | 7 | 1 | Unique
REC-018 | PRJ-002 | Cedar Clinic | Gqeberha | Infrastructure | A. Jacobs | Ndlovu Projects | Concrete | 2025-09-18 | 40 | 79 | 1411406.01 | Present | 1520814.75 | Present | Complete | 40 | On Hold | In Progress | Review | 2026-01-04 | 39 | Behind Schedule | 109408.74 | 7.752% | Over Budget | 109408.74 | 7.752% | Older | 4 | 1 | Unique
REC-019 | PRJ-019 | Summit Bridge | Johannesburg | Commercial | D. Smith | CapeBuild | Concrete | 2025-10-17 | 153 | 158 | 6091914.11 | Present |  | Missing | Actual Cost Missing | 70 | In Progress | In Progress | OK | 2025-10-20 | 5 | Behind Schedule |  |  | Missing Data | 0 | 0% | Latest | 3 | 1 | Unique | OK
REC-020 | PRJ-015 | Greenfield Mall | Johannesburg | Roadworks | Unknown | Mandla Construction | Timber | 2025-11-15 | 164 | 155 | 707879.51 | Present | 627589.8 | Present | Complete | 55 | In Progress | In Progress | OK | 2026-04-04 | -9 | Ahead of Schedule | -80289.71 | -11.34% | Under Budget | -80289.71 | -11.34% | Latest | 6 | 1 | Unique | OK
REC-021 | PRJ-010 | Summit Mall | Cape Town | Residential | B. Mokoena | CapeBuild | Bricks | 2025-11-10 | 155 | 140 | 4424145.02 | Present | 4677653.58 | Present | Complete | 10 | In Progress | Planning | Mismatch | 2026-04-14 | -15 | Ahead of Schedule | 253508.56 | 5.73% | Over Budget | 253508.56 | 5.73% | Latest | 4 | 1 | Unique | OK
REC-022 | PRJ-007 | Harbour Mall | Pretoria | Roadworks | A. Jacobs | BuildRight Ltd | Bricks | 2025-06-25 | 72 | 100 | 4213987.24 | Present | 3843122.44 | Present | Complete | 100 | Completed | Completed | OK | 2025-07-29 | 28 | Behind Schedule | -370864.8 | -8.801% | Under Budget | -370864.8 | -8.801% | Older | 3 | 1 | Unique
REC-023 | PRJ-009 | Metro Residences | Durban | Infrastructure | E. Dlamini | Mandla Construction | Timber | 2025-03-24 | 133 | 153 | 4660421.54 | Present | 4942160.02 | Present | Complete | 10 | Planning | Planning | OK | 2025-04-26 | 20 | Behind Schedule | 281738.48 | 6.045% | Over Budget | 281738.48 | 6.045% | Older | 3 | 1 | Unique
REC-024 | PRJ-002 | Riverside Clinic | Cape Town | Roadworks | E. Dlamini | UrbanWorks | Cement | 2025-06-07 | 113 | 155 | 6081800.07 | Present | 7700155.71 | Present | Complete |  | Completed | Planning | Mismatch | 2025-07-17 | 42 | Behind Schedule | 1618355.64 | 26.61% | Over Budget | 1618355.64 | 26.61% | Older | 4 | 1 | Unique
REC-025 | PRJ-008 | Riverside School | Cape Town | Residential | D. Smith | BuildRight Ltd | Timber | 2025-03-25 | 65 | 106 | 2826840.06 | Present | 2458447.2 | Present | Complete | 70 | On Hold | In Progress | Review | 2025-05-21 | 41 | Behind Schedule | -368392.86 | -13.03% | Under Budget | -368392.86 | -13.03% | Older | 3 | 1 | Unique
REC-026 | PRJ-007 | Riverside Bridge | Durban | Roadworks | A. Jacobs | CapeBuild | Bricks | 2025-08-24 | 109 | 113 | 5378352.38 | Present | 6538256.02 | Present | Complete | 40 | Planning | In Progress | Mismatch |  | 4 | Behind Schedule | 1159903.64 | 21.57% | Over Budget | 1159903.64 | 21.57% | Missing Date | 3 | 1 | Unique
REC-027 | PRJ-017 | Summit Residences | Cape Town | Infrastructure | D. Smith | CapeBuild | Roofing | 2025-07-24 | 157 | 163 | 6120232.13 | Present | 5126740.21 | Present | Complete | 55 | In Progress | In Progress | OK | 2025-10-13 | 6 | Behind Schedule | -993491.92 | -16.23% | Under Budget | -993491.92 | -16.23% | Older | 5 | 1 | Unique
REC-028 | PRJ-014 | Oak Residences | Gqeberha | Infrastructure | Unknown | CapeBuild | Timber | 2025-11-07 | 150 | 142 | 2657471.46 | Present | 2838960.87 | Present | Complete | 55 | Planning | In Progress | Mismatch | 2025-11-25 | -8 | Ahead of Schedule | 181489.41 | 6.829% | Over Budget | 181489.41 | 6.829% | Latest | 3 | 1 | Unique | OK
REC-029 | PRJ-011 | Oak Office Block | Pretoria | Roadworks | E. Dlamini | Mandla Construction | Steel | 2025-11-16 | 100 | 127 | 5550095.5 | Present | 6326426.94 | Present | Complete | 55 | Completed | In Progress | Mismatch | 2026-03-04 | 27 | Behind Schedule | 776331.44 | 13.99% | Over Budget | 776331.44 | 13.99% | Latest | 6 | 1 | Unique | OK
REC-030 | PRJ-013 | Summit Clinic | Durban | Infrastructure | E. Dlamini | CapeBuild | Timber | 2025-03-31 | 177 | 198 | 2130936.72 | Present | 2245940.41 | Present | Complete | 0 | On Hold | Planning | Review | 2025-07-23 | 21 | Behind Schedule | 115003.69 | 5.397% | Over Budget | 115003.69 | 5.397% | Older | 7 | 1 | Unique
REC-031 | PRJ-015 | Summit Office Block |  | Commercial | C. Naidoo | Uknown | Steel | 2025-04-20 | 150 | 165 | 5210846.24 | Present |  | Missing | Actual Cost Missing | 75 | Planning | In Progress | Mismatch | 2025-05-28 | 15 | Behind Schedule |  |  | Missing Data | 0 | 0% | Older | 6 | 1 | Unique
REC-032 | PRJ-001 | Riverside Bridge | Pretoria | Renovation | B. Mokoena | Mandla Construction | Roofing | 2025-01-24 | 82 | 97 | 4070462.33 | Present | 4739014.07 | Present | Complete | 100 | On Hold | Completed | Review | 2025-07-20 | 15 | Behind Schedule | 668551.74 | 16.42% | Over Budget | 668551.74 | 16.42% | Older | 4 | 1 | Unique
REC-033 | PRJ-001 | Harbour Clinic | Cape Town | Renovation | Unknown | UrbanWorks | Roofing | 2025-02-24 | 128 | 127 | 1349291.76 | Present | 1698735.42 | Present | Complete |  | On Hold | Planning | Review | 2025-07-10 | -1 | Ahead of Schedule | 349443.66 | 25.9% | Over Budget | 349443.66 | 25.9% | Older | 4 | 1 | Unique
REC-034 | PRJ-018 | Central Road Upgrade | Pretoria | Renovation | C. Naidoo | Mandla Construction | Roofing | 2025-11-01 | 101 | 146 | 4970312.58 | Present | 4976707.94 | Present | Complete |  | On Hold | Planning | Review | 2026-01-11 | 45 | Behind Schedule | 6395.36 | 0.1287% | Over Budget | 6395.36 | 0.1287% | Older | 7 | 1 | Unique
REC-035 | PRJ-017 | Summit Office Block | Durban | Renovation | A. Jacobs | Mandla Construction | Steel | 2025-09-06 | 180 | 180 | 1966234.04 | Present | 1609837.76 | Present | Complete | 55 | In Progress | In Progress | OK | 2025-11-05 | 0 | On Schedule | -356396.28 | -18.13% | Under Budget | -356396.28 | -18.13% | Older | 5 | 1 | Unique
REC-036 | PRJ-013 | Harbour Clinic | Pretoria | Renovation | E. Dlamini | BuildRight Ltd | Cement | 2025-03-20 | 74 | 63 | 2842924.35 | Present | 2687816.37 | Present | Complete | 100 | On Hold | Completed | Review | 2025-06-26 | -11 | Ahead of Schedule | -155107.98 | -5.456% | Under Budget | -155107.98 | -5.456% | Older | 7 | 1 | Unique
REC-037 | PRJ-016 | Central Clinic |  | Roadworks | D. Smith | Uknown | Timber | 2025-01-04 | 110 | 114 | 4959219.53 | Present | 5984409.11 | Present | Complete | 85 | In Progress | In Progress | OK | 2025-04-01 | 4 | Behind Schedule | 1025189.58 | 20.67% | Over Budget | 1025189.58 | 20.67% | Older | 8 | 1 | Unique
REC-038 | PRJ-013 | Harbour Mall | Pretoria | Commercial | D. Smith | Mandla Construction | Concrete | 2025-03-26 | 139 | 182 | 1047673.73 | Present |  | Missing | Actual Cost Missing | 0 | On Hold | Planning | Review |  | 43 | Behind Schedule |  |  | Missing Data | 0 | 0% | Missing Date | 7 | 1 | Unique
REC-039 | PRJ-013 | Oak School | Cape Town | Renovation | A. Jacobs | BuildRight Ltd | Concrete | 2025-06-17 | 74 | 88 | 2292786.28 | Present | 2661041.81 | Present | Complete | 85 | Completed | In Progress | Mismatch | 2025-09-15 | 14 | Behind Schedule | 368255.53 | 16.06% | Over Budget | 368255.53 | 16.06% | Older | 7 | 1 | Unique
REC-040 | PRJ-008 | Riverside Road Upgrade | Durban | Residential | E. Dlamini | Mandla Construction | Timber | 2025-02-05 | 30 | 63 | 443937.49 | Present | 401160.41 | Present | Complete | 0 | In Progress | Planning | Mismatch |  | 33 | Behind Schedule | -42777.08 | -9.636% | Under Budget | -42777.08 | -9.636% | Missing Date | 3 | 1 | Unique
REC-041 | PRJ-009 | Summit Mall | Gqeberha | Residential | C. Naidoo | Ndlovu Projects | Roofing | 2025-07-08 | 62 | 85 | 4045296.84 | Present | 4668122.17 | Present | Complete | 10 | Completed | Planning | Mismatch |  | 23 | Behind Schedule | 622825.33 | 15.4% | Over Budget | 622825.33 | 15.4% | Missing Date | 3 | 1 | Unique
REC-042 | PRJ-013 | Cedar Residences | Durban | Infrastructure | D. Smith | CapeBuild | Concrete | 2025-04-12 | 39 | 61 | 4566340.1 | Present | 4993846.33 | Present | Complete | 10 | Completed | Planning | Mismatch | 2025-08-20 | 22 | Behind Schedule | 427506.23 | 9.362% | Over Budget | 427506.23 | 9.362% | Older | 7 | 1 | Unique
REC-043 | PRJ-011 | Metro Bridge | Johannesburg | Infrastructure | C. Naidoo | Ndlovu Projects | Cement | 2025-01-07 | 127 | 164 | 3313760.66 | Present | 3303029.71 | Present | Complete | 70 | In Progress | In Progress | OK | 2025-05-11 | 37 | Behind Schedule | -10730.95 | -0.3238% | Under Budget | -10730.95 | -0.3238% | Older | 6 | 1 | Unique
REC-044 | PRJ-015 | Central Clinic | Pretoria | Infrastructure | E. Dlamini | UrbanWorks | Bricks | 2025-12-08 | 171 | 173 | 2264403.64 | Present | 2044184.92 | Present | Complete | 10 | Completed | Planning | Mismatch | 2025-08-20 | 2 | Behind Schedule | -220218.72 | -9.725% | Under Budget | -220218.72 | -9.725% | Older | 6 | 1 | Unique
REC-045 | PRJ-016 | Summit Residences | Gqeberha | Commercial | A. Jacobs | Mandla Construction | Roofing | 2025-06-16 | 66 | 82 | 1575749.06 | Present | 1857676.06 | Present | Complete | 70 | Completed | In Progress | Mismatch | 2025-09-29 | 16 | Behind Schedule | 281927 | 17.89% | Over Budget | 281927 | 17.89% | Older | 8 | 1 | Unique
REC-046 | PRJ-016 | Cedar School | Johannesburg | Renovation | B. Mokoena | CapeBuild | Roofing | 2025-10-12 | 81 | 110 | 3225581.94 | Present | 3664006.92 | Present | Complete | unknown | Planning | Unknown | Unknown | 2026-03-10 | 29 | Behind Schedule | 438424.98 | 13.59% | Over Budget | 438424.98 | 13.59% | Latest | 8 | 1 | Unique | OK
REC-047 | PRJ-012 | Greenfield Depot | Durban | Roadworks | C. Naidoo | Mandla Construction | Concrete | 2025-08-31 | 161 | 179 | 2398483.71 | Present | 3066019.46 | Present | Complete |  | Completed | Planning | Mismatch | 2025-10-20 | 18 | Behind Schedule | 667535.75 | 27.83% | Over Budget | 667535.75 | 27.83% | Older | 4 | 1 | Unique
REC-048 | PRJ-011 | Summit School |  | Commercial | C. Naidoo | Mandla Construction | Bricks | 2025-03-03 | 157 | 202 | 5013685.06 | Present | 4374815.85 | Present | Complete | 40 | In Progress | In Progress | OK | 2025-04-18 | 45 | Behind Schedule | -638869.21 | -12.74% | Under Budget | -638869.21 | -12.74% | Older | 6 | 1 | Unique
REC-049 | PRJ-010 | Metro Depot | Cape Town | Residential | E. Dlamini | CapeBuild | Timber | 2025-01-08 | 156 | 149 | 1964445.79 | Present | 2489242.5 | Present | Complete |  | Completed | Planning | Mismatch | 2025-05-11 | -7 | Ahead of Schedule | 524796.71 | 26.71% | Over Budget | 524796.71 | 26.71% | Older | 4 | 1 | Unique
REC-050 | PRJ-015 | Oak Depot | Cape Town | Infrastructure | A. Jacobs | Mandla Construction | Steel | 2025-06-24 | 67 | 55 | 1827989.94 | Present | 2213442.61 | Present | Complete | 10 | Planning | Planning | OK | 2025-11-16 | -12 | Ahead of Schedule | 385452.67 | 21.09% | Over Budget | 385452.67 | 21.09% | Older | 6 | 1 | Unique
REC-051 | PRJ-010 | Central Depot | Durban | Infrastructure | D. Smith | CapeBuild | Cement | 2025-02-13 | 83 | 75 | 3737956.47 | Present | 3693426.23 | Present | Complete | 40 | On Hold | In Progress | Review | 2025-07-22 | -8 | Ahead of Schedule | -44530.24 | -1.191% | Under Budget | -44530.24 | -1.191% | Older | 4 | 1 | Unique
REC-052 | PRJ-002 | Metro Clinic | Johannesburg | Infrastructure | A. Jacobs | Mandla Construction | Concrete | 2025-11-09 | 45 | 90 | 5017106.9 | Present | 5482481.27 | Present | Complete | 55 | Planning | In Progress | Mismatch | 2026-02-22 | 45 | Behind Schedule | 465374.37 | 9.276% | Over Budget | 465374.37 | 9.276% | Latest | 4 | 1 | Unique | OK
REC-053 | PRJ-015 | Cedar Clinic | Durban | Infrastructure | B. Mokoena | UrbanWorks | Concrete | 2025-11-01 | 140 | 143 | 453999.1 | Present | 419518.98 | Present | Complete | 55 | On Hold | In Progress | Review | 2026-03-21 | 3 | Behind Schedule | -34480.12 | -7.595% | Under Budget | -34480.12 | -7.595% | Older | 6 | 1 | Unique
REC-054 | PRJ-008 | Central Mall | Pretoria | Roadworks | D. Smith | CapeBuild | Cement | 2025-03-18 | 88 | 125 | 1138976.78 | Present | 922365.06 | Present | Complete |  | Completed | Planning | Mismatch | 2025-08-04 | 37 | Behind Schedule | -216611.72 | -19.02% | Under Budget | -216611.72 | -19.02% | Older | 3 | 1 | Unique
REC-055 | PRJ-016 | Harbour Mall | Johannesburg | Infrastructure | E. Dlamini | BuildRight Ltd | Roofing | 2025-08-13 | 40 | 63 | 499129.9 | Present |  | Missing | Actual Cost Missing | 70 | Completed | In Progress | Mismatch | 2025-10-21 | 23 | Behind Schedule |  |  | Missing Data | 0 | 0% | Older | 8 | 1 | Unique
REC-056 | PRJ-019 | Oak Depot | Cape Town | Renovation | C. Naidoo | UrbanWorks | Bricks | 2025-01-21 | 64 | 79 | 3493524.01 | Present | 3497418.25 | Present | Complete | 55 | In Progress | In Progress | OK | 2025-04-14 | 15 | Behind Schedule | 3894.24 | 0.1115% | Over Budget | 3894.24 | 0.1115% | Older | 3 | 1 | Unique
REC-057 | PRJ-004 | Central Mall | Cape Town | Roadworks | C. Naidoo | BuildRight Ltd | Timber | 2025-03-24 | 104 | 115 | 4585460.46 | Present | 4237464.81 | Present | Complete | 85 | Planning | In Progress | Mismatch | 2025-08-03 | 11 | Behind Schedule | -347995.65 | -7.589% | Under Budget | -347995.65 | -7.589% | Older | 3 | 1 | Unique
REC-058 | PRJ-001 | Harbour Clinic | Durban | Infrastructure | B. Mokoena | CapeBuild | Timber | 2025-10-05 | 138 | 149 | 588775.53 | Present | 611867.13 | Present | Complete | 100 | On Hold | Completed | Review | 2026-04-02 | 11 | Behind Schedule | 23091.6 | 3.922% | Over Budget | 23091.6 | 3.922% | Latest | 4 | 1 | Unique | OK
REC-059 | PRJ-016 | Harbour Bridge | Cape Town | Commercial | A. Jacobs | UrbanWorks | Concrete | 2025-03-04 | 27 | 52 | 4055447.92 | Present | 3648478.58 | Present | Complete | 25 | Completed | In Progress | Mismatch | 2025-08-17 | 25 | Behind Schedule | -406969.34 | -10.04% | Under Budget | -406969.34 | -10.04% | Older | 8 | 1 | Unique
REC-060 | PRJ-005 | Riverside Depot | Durban | Commercial | D. Smith | Mandla Construction | Cement | 2025-09-13 | 94 | 111 | 4658822.69 | Present | 4601729.62 | Present | Complete | 100 | On Hold | Completed | Review | 2026-01-22 | 17 | Behind Schedule | -57093.07 | -1.225% | Under Budget | -57093.07 | -1.225% | Latest | 7 | 1 | Unique | OK
REC-061 | PRJ-005 | Harbour School | Cape Town | Infrastructure | E. Dlamini | UrbanWorks | Steel | 2025-02-05 | 90 | 124 | 5187538.64 | Present | 5122545.07 | Present | Complete |  | Completed | Planning | Mismatch | 2025-05-31 | 34 | Behind Schedule | -64993.57 | -1.253% | Under Budget | -64993.57 | -1.253% | Older | 7 | 1 | Unique
REC-062 | PRJ-018 | Riverside Clinic | Gqeberha | Renovation | B. Mokoena | UrbanWorks | Concrete | 2025-09-05 | 108 | 114 | 3699483.86 | Present | 3890802.78 | Present | Complete | 100 | Completed | Completed | OK | 2025-11-26 | 6 | Behind Schedule | 191318.92 | 5.172% | Over Budget | 191318.92 | 5.172% | Older | 7 | 1 | Unique
REC-063 | PRJ-016 | Harbour Road Upgrade | Gqeberha | Infrastructure | C. Naidoo | BuildRight Ltd | Timber | 2025-07-15 | 118 | 145 | 5202460.38 | Present | 5753970.61 | Present | Complete | 25 | On Hold | In Progress | Review | 2025-08-10 | 27 | Behind Schedule | 551510.23 | 10.6% | Over Budget | 551510.23 | 10.6% | Older | 8 | 1 | Unique
REC-064 | PRJ-017 | Central School | Durban | Infrastructure | D. Smith | BuildRight Ltd | Bricks | 2025-08-22 | 23 | 54 |  | Missing | 1398967.1 | Present | Budget Missing | 25 | Planning | In Progress | Mismatch | 2026-02-11 | 31 | Behind Schedule | 1398967.1 |  | Missing Data | 0 | 0% | Older | 5 | 1 | Unique
REC-065 | PRJ-018 | Cedar Clinic | Durban | Commercial | A. Jacobs | UrbanWorks | Concrete | 2025-07-14 | 101 | 126 | 4741983.91 | Present | 5499283.03 | Present | Complete |  | Planning | Planning | OK | 2025-12-24 | 25 | Behind Schedule | 757299.12 | 15.97% | Over Budget | 757299.12 | 15.97% | Older | 7 | 1 | Unique
REC-066 | PRJ-004 | Summit Office Block | Durban | Roadworks | B. Mokoena | Mandla Construction | Cement | 2025-08-16 | 62 | 91 |  | Missing | 1685605.29 | Present | Budget Missing | 70 | Planning | In Progress | Mismatch |  | 29 | Behind Schedule | 1685605.29 |  | Missing Data | 0 | 0% | Missing Date | 3 | 1 | Unique
REC-067 | PRJ-019 | Metro Clinic | Pretoria | Commercial | D. Smith | CapeBuild | Roofing | 2025-04-03 | 63 | 59 | 743552.19 | Present | 903728.05 | Present | Complete | 40 | On Hold | In Progress | Review | 2025-04-06 | -4 | Ahead of Schedule | 160175.86 | 21.54% | Over Budget | 160175.86 | 21.54% | Older | 3 | 1 | Unique
REC-068 | PRJ-015 | Summit Depot | Durban | Commercial | Unknown | UrbanWorks | Concrete | 2025-05-28 | 159 | 154 | 711636.88 | Present | 891409.04 | Present | Complete | 75% | On Hold | Planning | Review | 2025-07-28 | -5 | Ahead of Schedule | 179772.16 | 25.26% | Over Budget | 179772.16 | 25.26% | Older | 6 | 1 | Unique
REC-069 | PRJ-013 | Summit Residences |  | Residential | E. Dlamini | UrbanWorks | Bricks | 2025-10-20 | 111 | 132 |  | Missing | 2371342.08 | Present | Budget Missing | 0 | On Hold | Planning | Review | 2025-12-18 | 21 | Behind Schedule | 2371342.08 |  | Missing Data | 0 | 0% | Older | 7 | 1 | Unique
REC-070 | PRJ-020 | Harbour School | Pretoria | Residential | E. Dlamini | CapeBuild | Roofing | 2025-06-30 | 76 | 101 | 1438324.93 | Present | 1302134.83 | Present | Complete | 25 | Planning | In Progress | Mismatch | 2025-08-03 | 25 | Behind Schedule | -136190.1 | -9.469% | Under Budget | -136190.1 | -9.469% | Older | 4 | 1 | Unique
REC-071 | PRJ-003 | Summit Road Upgrade | Durban | Renovation | Unknown | CapeBuild | Concrete | 2025-06-01 | 103 | 135 | 2846894.33 | Present | 2506398.36 | Present | Complete |  | Completed | Planning | Mismatch | 2025-09-29 | 32 | Behind Schedule | -340495.97 | -11.96% | Under Budget | -340495.97 | -11.96% | Older | 4 | 1 | Unique
REC-072 | PRJ-003 | Cedar Bridge | Cape Town | Roadworks | E. Dlamini | BuildRight Ltd | Timber | 2025-03-14 | 77 | 117 | 4477023.28 | Present | 5001744.36 | Present | Complete | 85 | Completed | In Progress | Mismatch | 2025-06-17 | 40 | Behind Schedule | 524721.08 | 11.72% | Over Budget | 524721.08 | 11.72% | Older | 4 | 1 | Unique
REC-073 | PRJ-009 | Harbour Office Block | Gqeberha | Commercial | A. Jacobs | UrbanWorks | Roofing | 2025-10-27 | 117 | 154 | 4240932.92 | Present | 4095625.07 | Present | Complete | 40 | On Hold | In Progress | Review | 2026-01-13 | 37 | Behind Schedule | -145307.85 | -3.426% | Under Budget | -145307.85 | -3.426% | Older | 3 | 1 | Unique
REC-074 | PRJ-014 | Cedar Clinic | Johannesburg | Commercial | D. Smith | UrbanWorks | Bricks | 2025-03-01 | 55 | 42 |  | Missing | 5746097.1 | Present | Budget Missing |  | Planning | Planning | OK | 2025-08-20 | -13 | Ahead of Schedule | 5746097.1 |  | Missing Data | 0 | 0% | Older | 3 | 1 | Unique
REC-075 | PRJ-018 | Oak School | Cape Town | Roadworks | B. Mokoena | UrbanWorks | Timber | 2025-08-03 | 170 | 202 | 4791244.69 | Present | 5858287.9 | Present | Complete | 10 | On Hold | Planning | Review | 2025-10-03 | 32 | Behind Schedule | 1067043.21 | 22.27% | Over Budget | 1067043.21 | 22.27% | Older | 7 | 1 | Unique
REC-076 | PRJ-012 | Summit Clinic | Cape Town | Renovation | A. Jacobs | Mandla Construction | Roofing | 2025-02-20 | 114 | 133 | 5885601.33 | Present | 6488365.8 | Present | Complete | 0 | On Hold | Planning | Review | 2025-08-03 | 19 | Behind Schedule | 602764.47 | 10.24% | Over Budget | 602764.47 | 10.24% | Older | 4 | 1 | Unique
REC-077 | PRJ-020 | Riverside Clinic | Johannesburg | Roadworks | B. Mokoena | Ndlovu Projects | Concrete | 2025-01-11 | 32 | 67 |  | Missing | 2975024.83 | Present | Budget Missing | 40 | Planning | In Progress | Mismatch | 2025-03-23 | 35 | Behind Schedule | 2975024.83 |  | Missing Data | 0 | 0% | Older | 4 | 1 | Unique
REC-078 | PRJ-005 | Harbour Office Block | Johannesburg | Infrastructure | Unknown | BuildRight Ltd | Steel | 2025-03-08 | 158 | 159 | 5240711.4 | Present | 4375801.02 | Present | Complete | 0 | In Progress | Planning | Mismatch | 2025-05-15 | 1 | Behind Schedule | -864910.38 | -16.5% | Under Budget | -864910.38 | -16.5% | Older | 7 | 1 | Unique
REC-079 | PRJ-002 | Cedar Depot | Gqeberha | Commercial | E. Dlamini | BuildRight Ltd | Roofing | 2025-03-06 | 127 | 145 | 960308.17 | Present |  | Missing | Actual Cost Missing | 100 | Completed | Completed | OK | 2025-08-22 | 18 | Behind Schedule |  |  | Missing Data | 0 | 0% | Older | 4 | 1 | Unique
REC-080 | PRJ-017 | Oak Mall | Pretoria | Renovation | A. Jacobs | BuildRight Ltd | Bricks | 2025-06-04 | 137 | 163 | 6275163.64 | Present | 5085472.33 | Present | Complete | 100 | On Hold | Completed | Review | 2025-11-07 | 26 | Behind Schedule | -1189691.31 | -18.96% | Under Budget | -1189691.31 | -18.96% | Older | 5 | 1 | Unique
REC-081 | PRJ-005 | Summit Depot | Gqeberha | Infrastructure | D. Smith | BuildRight Ltd | Roofing | 2025-02-03 | 52 | 54 |  | Missing | 4453760.3 | Present | Budget Missing | 70 | On Hold | In Progress | Review | 2025-03-05 | 2 | Behind Schedule | 4453760.3 |  | Missing Data | 0 | 0% | Older | 7 | 1 | Unique
REC-082 | PRJ-018 | Oak Mall | Durban | Renovation | C. Naidoo | CapeBuild | Bricks | 2025-04-21 | 130 | 143 | 5800568.89 | Present | 5724620.8 | Present | Complete | 100 | On Hold | Completed | Review | 2025-05-31 | 13 | Behind Schedule | -75948.09 | -1.309% | Under Budget | -75948.09 | -1.309% | Older | 7 | 1 | Unique
REC-083 | PRJ-016 | Harbour Office Block | Cape Town | Renovation | C. Naidoo | UrbanWorks | Roofing | 2025-04-02 | 43 | 81 | 783527.23 | Present | 780344.75 | Present | Complete | 70 | In Progress | In Progress | OK | 2025-02-18 | 38 | Behind Schedule | -3182.48 | -0.4062% | Under Budget | -3182.48 | -0.4062% | Older | 8 | 1 | Unique
REC-084 | PRJ-010 | Riverside Mall | Durban | Infrastructure | C. Naidoo | BuildRight Ltd | Bricks | 2025-11-04 | 99 | 106 | 897503.54 | Present | 927755.04 | Present | Complete | 25 | On Hold | In Progress | Review | 2026-03-31 | 7 | Behind Schedule | 30251.5 | 3.371% | Over Budget | 30251.5 | 3.371% | Older | 4 | 1 | Unique
REC-085 | PRJ-008 | Summit Residences | Johannesburg | Roadworks | C. Naidoo | CapeBuild | Bricks | 2025-08-08 | 163 | 197 | 5365167.87 | Present | 5830792.76 | Present | Complete |  | Planning | Planning | OK | 2025-08-10 | 34 | Behind Schedule | 465624.89 | 8.679% | Over Budget | 465624.89 | 8.679% | Latest | 3 | 1 | Unique | OK
REC-086 | PRJ-006 | Riverside Bridge | Pretoria | Renovation | C. Naidoo | Mandla Construction | Bricks | 2025-03-15 | 164 | 191 | 2754902.15 | Present | 2344249.07 | Present | Complete |  | Planning | Planning | OK | 2025-06-03 | 27 | Behind Schedule | -410653.08 | -14.91% | Under Budget | -410653.08 | -14.91% | Older | 4 | 1 | Unique
REC-087 | PRJ-011 | Summit Depot | Cape Town | Renovation | E. Dlamini | UrbanWorks | Timber | 2025-10-18 | 172 | 162 | 5770888.65 | Present | 4950210.3 | Present | Complete | 0 | Planning | Planning | OK | 2025-12-27 | -10 | Ahead of Schedule | -820678.35 | -14.22% | Under Budget | -820678.35 | -14.22% | Older | 6 | 1 | Unique
REC-088 | PRJ-007 | Harbour Clinic | Pretoria | Infrastructure | A. Jacobs | BuildRight Ltd | Steel | 2025-09-20 | 49 | 56 | 2936960.21 | Present | 2706770.77 | Present | Complete | 100 | Completed | Completed | OK | 2025-12-07 | 7 | Behind Schedule | -230189.44 | -7.838% | Under Budget | -230189.44 | -7.838% | Latest | 3 | 1 | Unique | OK
REC-089 | PRJ-007 | Metro Bridge | Gqeberha | Commercial | E. Dlamini | Ndlovu Projects | Roofing | 2025-03-12 | 85 | 88 | 2300764.72 | Present | 1803488.83 | Present | Complete | 85 | In Progress | In Progress | OK | 2025-06-11 | 3 | Behind Schedule | -497275.89 | -21.61% | Under Budget | -497275.89 | -21.61% | Older | 3 | 1 | Unique
REC-090 | PRJ-003 | Oak Bridge | Durban | Residential | D. Smith | BuildRight Ltd | Bricks | 2025-07-23 | 30 | 42 | 367134.6 | Present | 455460.29 | Present | Complete | 70 | On Hold | In Progress | Review | 2025-09-05 | 12 | Behind Schedule | 88325.69 | 24.06% | Over Budget | 88325.69 | 24.06% | Older | 4 | 1 | Unique
REC-091 | PRJ-020 | Cedar Bridge | Durban | Roadworks | B. Mokoena | CapeBuild | Steel | 2025-08-24 | 112 | 102 | 2979448.62 | Present | 2481676.81 | Present | Complete | 85 | On Hold | In Progress | Review | 2025-09-13 | -10 | Ahead of Schedule | -497771.81 | -16.71% | Under Budget | -497771.81 | -16.71% | Latest | 4 | 1 | Unique | OK
REC-092 | PRJ-017 | Metro Clinic | Cape Town | Residential | C. Naidoo | Mandla Construction | Steel | 2025-11-21 | 49 | 67 | 3437200.39 | Present |  | Missing | Actual Cost Missing | 70 | On Hold | In Progress | Review | 2026-04-25 | 18 | Behind Schedule |  |  | Missing Data | 0 | 0% | Latest | 5 | 1 | Unique | OK
REC-093 | PRJ-005 | Greenfield Road Upgrade | Pretoria | Residential | D. Smith | UrbanWorks | Roofing | 2025-02-08 | 65 | 110 | 5080300.56 | Present | 5217765.94 | Present | Complete | 100 | Completed | Completed | OK | 2025-04-27 | 45 | Behind Schedule | 137465.38 | 2.706% | Over Budget | 137465.38 | 2.706% | Older | 7 | 1 | Unique
REC-094 | PRJ-009 | Harbour Office Block | Durban | Residential | Unknown | Ndlovu Projects | Cement | 2025-10-30 | 34 | 41 | 3420855.53 | Present | 3199197.52 | Present | Complete | 100 | Planning | Completed | Mismatch | 2026-03-09 | 7 | Behind Schedule | -221658.01 | -6.48% | Under Budget | -221658.01 | -6.48% | Latest | 3 | 1 | Unique | OK
REC-095 | PRJ-013 | Riverside Office Block | Gqeberha | Renovation | E. Dlamini | Mandla Construction | Concrete | 2025-08-25 | 168 | 188 | 6213946.73 | Present | 7142686.46 | Present | Complete | 0 | On Hold | Planning | Review | 2025-12-19 | 20 | Behind Schedule | 928739.73 | 14.95% | Over Budget | 928739.73 | 14.95% | Latest | 7 | 1 | Unique | OK
REC-096 | PRJ-004 | Metro Office Block | Durban | Roadworks | D. Smith | UrbanWorks | Bricks | 2025-06-25 | 41 | 58 | 4288294.32 | Present | 3428796.05 | Present | Complete | 100 | On Hold | Completed | Review | 2025-12-16 | 17 | Behind Schedule | -859498.27 | -20.04% | Under Budget | -859498.27 | -20.04% | Latest | 3 | 1 | Unique | OK
REC-097 | PRJ-020 | Summit Road Upgrade | Durban | Residential | E. Dlamini | Mandla Construction | Bricks | 2025-01-27 | 105 | 94 | 2310567.22 | Present | 2446848.19 | Present | Complete | 85 | Completed | In Progress | Mismatch | 2025-04-17 | -11 | Ahead of Schedule | 136280.97 | 5.898% | Over Budget | 136280.97 | 5.898% | Older | 4 | 1 | Unique
REC-098 | PRJ-013 | Metro Mall | Pretoria | Renovation | C. Naidoo | BuildRight Ltd | Bricks | 2025-03-08 | 172 | 202 | 6112513.75 | Present | 5713922.5 | Present | Complete | 85 | Completed | In Progress | Mismatch | 2025-05-27 | 30 | Behind Schedule | -398591.25 | -6.521% | Under Budget | -398591.25 | -6.521% | Older | 7 | 1 | Unique
REC-099 | PRJ-006 | Cedar School | Johannesburg | Infrastructure | E. Dlamini | Ndlovu Projects | Concrete | 2025-04-20 | 107 | 152 | 5038476.3 | Present | 4413718.42 | Present | Complete | 25 | In Progress | In Progress | OK | 2025-10-07 | 45 | Behind Schedule | -624757.88 | -12.4% | Under Budget | -624757.88 | -12.4% | Older | 4 | 1 | Unique
[21 empty] | 17.0303 |  | 30610763.5 |  | 46
[11 empty] | 309616714.23 |  | 322980405.19
7127514.04
13363690.96

## Business_Insights
Area | Key Finding | Business Impact | Recommendation
55% Cost | 11 of the 20 projects are recorded as over budget |  | Investigate cost variances, review estimates and approved changes, and monitor actual expenditure against budgets
70% Schedule | 14 of the 20 projects are recorded as behind schedule |  | Review delayed activities, resource availability, subcontractor dependencies, and differences between planned and actual duration.
70% Data quality | 14 projects are marked either Review or Mismatch |  | Reconcile recorded project statuses with progress percentages and confirm whether projects marked On Hold need separate treatment
2 Missing data | Two latest project records are classified as Missing Data in the budget-status pivot |  | Obtain the missing budget or actual cost figures before drawing conclusions about those projects' financial performance

## Analysis_Methodology
Step | Methodology
1. Data cleaning | Standardised project types, site locations, project statuses and contractor names. Corrected inconsistent text formatting.
2. Data quality checks | Checked Record_ID uniqueness, investigated a suspected duplicate record, and created flags for missing budget and actual cost data.
3. Calculated columns | Calculated schedule variance, cost variance, cost variance percentage, budget status, expected project status and status validation flags
4. Latest-record analysis | Identified the latest dated tracking record for each Project_ID to represent its latest recorded position.
5.Pivot table analysis | Summarised budget performance, schedule performance, expected project status and status-validataion results.
6. Dashboard and recommendations | Created KPI cards and four charts, then documented business findings and recommendation follow-up actions
• Duplicate handling: Two records for PRJ-001 had the same latest date and appeared identical apart from Record_ID (REC-058 and REC-158).
• Limitations: The analysis represents the latest available tracking records, not necessarily verified final project outcomes. Missing cost data and status inconsistencies may affect interpretation.

## Data_Cleaning_Process
Cleaning Activity | What I Did
Standardised text | Used consistent spelling and formatting for site locations, project types, project statuses and contractor names.
Date standardisation | Used Short Date to standardise date columns
Handled missing values | Created missing-data flags for budget and actual cost fields rather than assuming missing values zero. Replaced missing categorical values with Unknown while retaining numericc values for appropriate treatment during analysis.
Checked record identifiers | Verified that Record_ID values were unique and investigated a suspected duplicate tracking record (REC-158).
Validated project status | Compared recorded project statuses with progress percentages using defined business rules.
Checked cost performance | Calculated schedule variance as actual duration minus planned duration.
Identified latest records | Used Last_Updated to identify the latest dated tracking record for each project.
Preserved data lineage | Retained the original raw dataset and conducted analysis using a separate working copy.

## PT_Project_Overview
Project Overview
Project_Status | Project_Count
Completed | 15
In Progress | 11
On Hold | 17
Planning | 15
Grand Total | 20
Schedule Performance
Project_Type | Unique_Project_Count | Avg_Schedule_Variance | Schedule_Variance_Count
Commercial | 11 | 15.8667 | 15
Infrastructure | 14 | 16.28 | 25
Renovation | 11 | 19.3478 | 23
Residential | 11 | 12.2941 | 17
Roadworks | 12 | 20.3684 | 19
Grand Total | 20 | 17.0303 | 99
Schedule Status
Schedule_Status | Unique_Project_Count
Ahead of Schedule | 11
Behind Schedule | 20
On Schedule | 3
Grand Total | 20
Cost Performance -All Records
Project_Type | Unique_Project_Count | Budget_ZAR_Sum | Actual_Cost_ZAR_Sum | Cost_Variance_Sum | Avg_Cost_Variance_Percentage
Commercial | 11 | 44522221.78 | 37049262.24 | 91685.61 | 3.072%
Infrastructure | 14 | 78058070.34 | 82348900.02 | -1062767.82 | -0.4928%
Renovation | 11 | 85538614.31 | 85793731.75 | 255117.44 | 0.5843%
Residential | 11 | 36783834.4 | 40919556.17 | 1994194.43 | 3.321%
Roadworks | 12 | 66359040.51 | 76868955.01 | 5849284.38 | 5.216%
Grand Total | 20 | 311261781.34 | 322980405.19 | 7127514.04 | 2.048%
Cost_Performance-Complete Records Only
Cost_Data _Flag | Complete
Project_Type | Unique_Project_Count | Budget_ZAR_Sum | Actual_Cost_ZAR_Sum | Cost_Variance_Sum | Avg_Cost_Variance_Percentage
Commercial | 9 | 31211479.53 | 31303165.14 | 91685.61 | 4.608%
Infrastructure | 14 | 77558940.44 | 76496172.62 | -1062767.82 | -0.5599%
Renovation | 11 | 85538614.31 | 85793731.75 | 255117.44 | 0.5843%
Residential | 7 | 31701566.9 | 33695761.33 | 1994194.43 | 4.705%
Roadworks | 12 | 66359040.51 | 72208324.89 | 5849284.38 | 5.829%
Grand Total | 20 | 292369641.69 | 299497155.73 | 7127514.04 | 2.414%
Budget Status - Tracking History
Budget_Status | Unique_Project_Count
Missing Data | 11
Over Budget | 18
Under Budget | 17
Grand Total | 20
Contractor Performance
Main_Contractor | Unique_Project_Count | Avg_Schedule_Variance | Avg_Cost_Variance
BuildRight Ltd | 13 | 16.0455 | -77068.7536
CapeBuild | 15 | 13.2727 | 70687.9868
Mandla Construction | 16 | 19.56 | 163767.1684
Ndlovu Projects | 8 | 25.2222 | -78786.48
Uknown | 2 | 9.5 | 512594.79
UrbanWorks | 13 | 16.1053 | 150400.0232
Grand Total | 20 | 17.0303 | 71995.0913
Location Performance
Site_Location | Unique_Project_Count | Avg_Schedule_Variance | Avg_Cost_Variance
| 4 | 21.25 | 96580.0925
Cape Town | 16 | 14.1818 | 158225.3595
Durban | 14 | 12.5217 | 58089.5604
Gqeberha | 10 | 14.375 | 245501.4819
Johannesburg | 12 | 21.9231 | -35659.4462
Pretoria | 15 | 23.1429 | -73346.4305
Grand Total | 20 | 17.0303 | 71995.0913
Data Quality
Cost_Data_Flag | Unique_Project_Count
Actual Cost Missing | 7
Budget Missing | 7
Complete | 20
Grand Total | 20
Budget Status - Current
Latest_Record_Flag | Latest
Budget_Status | Project_Count
Missing Data | 2
Over Budget | 11
Under Budget | 7
Grand Total | 20
Schedule Status - Current
Latest_Record_Flag | Latest
Schedule_Status | Project_Count
Ahead of Schedule | 6
Behind Schedule | 14
Grand Total | 20
Expected Project Status - Current
Latest_Record_Flag | Latest
Project_Expected_Status | Project_Count
Completed | 6
In Progress | 9
Planning | 4
Unknown | 1
Grand Total | 20
Project_Status_Check
Latest_Record_Flag | Latest
Project_Status_Check | Project_Count
Mismatch | 7
OK | 5
Review | 7
Unknown | 1
Grand Total | 20

## Dashboard
CONSTRUCTION PROJECT CONTROLS & PERFORMANCE DASHBOARD
Latest Recorded Project Position | Budget, Schedule & Status Quality
Total Projects
20
latest recorded project position
Over Budget
55%
11 of 20 latest recorded projects
Behind Schedule
70%
14 of 20 latest recorded projects
Review/Mismatch
70%
14 of 20 latest recorded projects

## Project_Workflow_&_Analysis_Not
ROADMAP : Messy data > Cleaned data > Data quality validation > Calculated fields > Pivot analysis > Dashboard
Analysis Questions:
1. How many projects are there and what is their current status
2.Which projext types have the most schedule problems?
3. Which project types have the greatest cost problems?
4. Which contractors are performing well or poorly?
5. Which locations have the most projects and delays?
6. How much budget vs actual cost is being spent?
7. Which projects have the largest cost overruns?
8. How many projects have missing financial data?
Steps Taken:
Converted the worksheet range into a table to create a dynamic database
Standardised the Site Location, Project Status and Project Type columns
Replaced missing categorical values with "Unknown" while retaining missing numeric values for appropiate treatment during analysis.
Standardise Main Contractor column
Used the Short Date to standardise the Start Date and Last Updated column
Converted Planned Duration Days & Actual Duration Days from mixed text and numbers to all numeric values
Missing financial values (Budgeted Zar and Actual Cost Zar) were not automatically replaced because doing so could introduce artificial values and distort cost analysis.
Standardised the Progress Percent column to numbers between 0 to 100. Created a helper column to populate missing values
Formatted the financial value columns from numeric to Zar (rands)
Created a Cost Variance Pivot helper column for pivot table aggregation
20 unique projects with 100 tracking records (record IDs). That's why my pivot calculations shows a grand total total of 20
Checked REC-158 as a possible duplicate for REC- 058 and removed it from the table
Calculated Columns:
1.Cost Variance
2. Cost Variance Percentage
3. Budget Status
4. Budget Missing
5. Actual Cost Missing
6. Cost Data Flag
7. Project Expected Status
8. Project Status Check
. Schedule Variance
10. Schedule Status
11. Latest Record Flag
Problems Incountered:
Progress Percent and Project Status column had contradicting data so l created 2 flagging columns (Expected Status and Status Check) to determine data that needed investigating
Could not format Cost Variance and Cost Variance Percentage in my pivot table because Excel treated the formula =IF(OR(ISBLANK(N2),ISBLANK(L2)),"",N2-L2) as text so l create Cost Variance Pivot and Cost Variance Percentage Pivot for pivot table aggregation
Realized disrepancies in my Cost Performance pivot table. Validated by filtering on Cost Data Flag column (Complete) then used Subtotal to calculate total Actual Cost, total Budget and total Cost Variance columns instead of Sum. However the budget and actual cost total increased in the Pivot Table grand total because it includes records with a budget or actual cost even when the other field is missing whereas the Complete records (SUBTOTAL) returns zero for those incomplete records
The Infrastructure project type Cost Variance in my Cost Performance Pivot Table mixed two different groups of records: (1. Budget and Actual Cost sums included records even when one value is missing. 2. Cost Variance sums only records where both Budget and Actual Cost are available.) To fix this l created a duplicated table filtering on the Cost Data Flag (Complete)
Pivot Tables:
NB//: Grand Total shows 20 but the values shows >20. There is no error - the data contains multiple tracking records per project. A project can appear more than one budget status across its tracking history eg a project might have missing cost data in one record and be over budget in a later record
1. Project Overview
2. Schedule Performance
3. Schedule Status
4. Cost Performance - All records
5. Cost Performance - Complete records only
6. Budget Status - Tracking History
7. Contractor Performance
8. Location Performance
9. Data Quality
10. Budget Status - Current
11. Schedule Status - Current
12. Expected Project Status - Current
13. Project Status Check
Dashboard:
KPI Cards:
Total Projects
Over Budget
Behind Schedule
Review/Mismatch
Charts
Current Budget Status
Latest Recorded Schedule Status
Expected Project Status - Latest Recorded
Project Status Check - Latest Recorded

## Data_Dictionary
Column | Meaning | Expected_Format | Cleaning_Notes
Record_ID | Unique row identifier | Text | Should be unique; check duplicates.
Project_ID | Project reference; may repeat across work records | Text | Standardize format; repeated IDs are expected.
Project_Name | Project/site project label | Text | Check spelling and inconsistent naming.
Site_Location | City/site location | Text | Standardize values (e.g., Cape Town, Johannesburg).
Project_Type | Construction work category | Text | Standardize categories (e.g., Roadworks, Infrastructure).
Project_Manager | Responsible project manager | Text | Identify blanks and decide whether to label Unknown.
Main_Contractor | Primary contractor | Text | Standardize contractor names.
Material_Category | Primary material category | Text | Categorical field for analysis.
Start_Date | Project start date | Date/text mixed | Normalize to a consistent date format.
Planned_Duration_Days | Planned project duration | Number/text mixed | Convert to numeric; validate positive values.
Actual_Duration_Days | Actual project duration | Number/text mixed | Convert to numeric; compare with plan.
Budget_ZAR | Approved budget in South African rand | Currency/blank | Handle missing values; don't assume zero.
Actual_Cost_ZAR | Recorded actual cost in rand | Currency/blank | Handle missing values; compare with budget.
Progress_Percent | Completion progress | Percent/text mixed | Normalize to numeric percentage from 0 to 100.
Project_Status | Current status | Text inconsistent | Standardize Planning, In Progress, Completed, On Hold.
Last_Updated | Date of latest status update | Date/blank | Normalize dates and inspect missing values.

## Project_Brief
Project Brief
Portfolio exercise: Construction Project Controls — Data Cleaning & Analysis
Business scenario: A construction company tracks project schedules, budgets, costs, progress, contractors and sites in a manually maintained spreadsheet.
Dataset: 100 rows of intentionally messy, synthetic records. No real company or person data is used.
Suggested workflow:
1. Preserve Raw_Data unchanged; create a separate Cleaned_Data sheet.
2. Profile blanks, duplicates, inconsistent labels, mixed date formats, numeric-as-text values and invalid progress entries.
3. Standardize categories and contractor/site names; convert dates and numeric fields; document assumptions.
4. Add calculated columns: Schedule_Variance_Days = Actual_Duration_Days - Planned_Duration_Days; Cost_Variance_ZAR = Actual_Cost_ZAR - Budget_ZAR; Cost_Variance_Pct = Cost_Variance_ZAR / Budget_ZAR; Budget_Status; Schedule_Status.
5. Build pivot tables by Project_Type, Site_Location, Project_Manager, Main_Contractor and Project_Status.
6. Suggested pivot charts: budget vs actual cost by project type; average schedule variance by site; project count by status; contractor cost variance.
7. Dashboard ideas: KPI cards (project count, total budget, total actual cost, average schedule variance, over-budget count), slicers for site/type/status/manager, and 3–4 pivot charts.
Analysis prompts: Which project types have the largest cost variance? Which sites show the longest delays? How does progress relate to project status? Which contractors have the most over-budget projects?
Important: Project_ID repeats are expected because the data represents project tracking records; investigate duplicate Record_IDs or exact duplicate rows separately.
All amounts are in ZAR. Treat missing budget/cost/progress as missing, not zero, unless your documented business rule says otherwise.